## ACAT 1C MS A,B,C,FRP
Army Cost Position Development Timeline Planner (ACAT 1C)
The DoDI 5000.73 contains timelines developed by the OSD CAPE for submission of documents to support Milestone Reviews and are tied to the OSD OIPT. HQDA and the Program Office must complete the Cost Analysis and Affordability Analysis in time to support the Army OIPT. The dates in this timeline planner were developed to be as consistent as possible with the OSD timelines but provide the Army staff sufficient time to complete the required analyses to inform the Army staff at the Army OIPT.
Early Milestone notification to the CAPE is essential because they will decide whether to develop the statutory ICE or delegate it to DASA-CE
CRB ACP Review occurs 90 Days after PEO approved CARD is briefed to the CRB
Enter desired Army OIPT Date and the rest of the dates will automatically calculate
ACAT 1C and below Reviews |  | Measured from CRB Date |  |  | Measured from Army OIPT Date
1 | Notify CAPE of Upcoming Milestone | CRB - | 210 | 2015-11-18 | OIPT - | 231 | 2015-11-18
2 | Draft CARD Submitted to ASA(ALT)/DASA-CE/CAPE | CRB - | 180 | 2015-12-18 | OIPT - | 201 | 2015-12-18
3 | PM/CRBWG Cost WIPT with CAPE | CRB - | 180 | 2015-12-18 | OIPT - | 201 | 2015-12-18
4 | CA Determination to Review Component ICE or Prepare CA ICE | CRB - | 165 | 2016-01-02 | OIPT - | 186 | 2016-01-02
5 | PEO Approved CARD Submission to ASA(ALT) | CRB - | 128 | 2016-02-08 | OIPT - | 149 | 2016-02-08
6 | CARD Brief to CRB Working Group | CRB - | 100 | 2016-03-07 | OIPT - | 121 | 2016-03-07
7 | CCA/ICE Methodology Brief to DASA-CE/CA | CRB - | 92 | 2016-03-15 | OIPT - | 113 | 2016-03-15
8 | CARD Brief to CRB | CRB - | 90 | 2016-03-17 | OIPT - | 111 | 2016-03-17
9 | Deliver CARD with CRB Updates to CA | CRB - | 45 | 2016-05-01 | OIPT - | 66 | 2016-05-01
10 | CCA/ICE Results Brief to DASA-CE/CA | CRB - | 40 | 2016-05-06 | OIPT - | 61 | 2016-05-06
11 | POE and CCA/ICE Submission | CRB - | 37 | 2016-05-09 | OIPT - | 58 | 2016-05-09
12 | CRB Working Group Kick-Off (POE/ICE presented to CRBWG/CA) | CRB - | 30 | 2016-05-16 | OIPT - | 51 | 2016-05-16
13 | Recommended ACP to DASA-CE | CRB - | 6 | 2016-06-09 | OIPT - | 27 | 2016-06-09
14 | CRB | CRB | 0 | 2016-06-15 | OIPT - | 21 | 2016-06-15
15 | Deliver Final ICE and ACP to CA | CRB | 0 | 2016-06-15 | OIPT - | 21 | 2016-06-15
16 | Army OIPT | CRB + | 21 | 2016-07-06 | OIPT | 0 | 2016-07-06 | Enter Date
17 | ASARC | CRB + | 35 | 2016-07-20 | OIPT + | 14 | 2016-07-20
The Draft CARD submitted to ASA(ALT)/DASA-CE/CA 180 days prior to the CRB (201 days prior to the Army OIPT) does not require PEO signature
The CARD submitted to ASA(ALT) 128 days prior to the CRB (149 days prior to the Army OIPT) does require PEO signature
DoDI 5000.73 bases dates on the OSD OIPT, these dates are based on the Army OIPT
DoDI 5000.73 requires delivery of the final CARD 21 days prior to the CRB. The final CARD will not be provided until the CRB reviews the recommended ACP
CA - Cost Assessment Directorate of CAPE
ICE - Independent Cost Estimate
CCA - Component Cost Assessment

## ACAT 1D MS A,B,C,FRP
Army Cost Position Development Timeline Planner (ACAT 1D)
The DoDI 5000.73 contains timelines developed by the OSD CAPE for submission of documents to support Milestone Reviews and are tied to the OSD OIPT. HQDA and the Program Office must complete the Cost Analysis and Affordability Analysis in time to support the Army OIPT. The dates in this timeline planner were developed to be as consistent as possible with the OSD timelines but provide the Army staff sufficient time to complete the required analyses to inform the Army staff at the Army OIPT.
CRB ACP Review occurs 90 Days after PEO approved CARD is briefed to the CRB
Enter desired Army OIPT Date and the rest of the dates will automatically calculate
ACAT 1D |  | Measured from CRB Date |  |  | Measured from Army OIPT Date
1 | Notify CAPE of Upcoming Milestone | CRB - | 210 | 2015-09-16 | OIPT - | 231 | 2015-09-16
2 | Draft CARD Submitted to ASA(ALT)/DASA-CE/CAPE | CRB - | 180 | 2015-10-16 | OIPT - | 201 | 2015-10-16
3 | PM/CRBWG Cost WIPT with CAPE | CRB - | 180 | 2015-10-16 | OIPT - | 201 | 2015-10-16
4 | PEO Approved CARD Submission to ASA(ALT) | CRB - | 128 | 2015-12-07 | OIPT - | 149 | 2015-12-07
5 | CARD Brief to CRB Working Group | CRB - | 100 | 2016-01-04 | OIPT - | 121 | 2016-01-04
6 | CCA Methodology Brief to DASA-CE | CRB - | 92 | 2016-01-12 | OIPT - | 113 | 2016-01-12
7 | CARD Brief to CRB | CRB - | 90 | 2016-01-14 | OIPT - | 111 | 2016-01-14
8 | Deliver CARD with CRB Updates to CA | CRB - | 45 | 2016-02-28 | OIPT - | 66 | 2016-02-28
9 | CCA Results Brief to DASA-CE | CRB - | 40 | 2016-03-04 | OIPT - | 61 | 2016-03-04
10 | POE/CCA Submission | CRB - | 37 | 2016-03-07 | OIPT - | 58 | 2016-03-07
11 | CRB Working Group Kick-Off (POE/ICE presented to CRBWG) | CRB - | 30 | 2016-03-14 | OIPT - | 51 | 2016-03-14
12 | Recommended ACP to DASA-CE | CRB - | 6 | 2016-04-07 | OIPT - | 27 | 2016-04-07
13 | CRB | CRB | 0 | 2016-04-13 | OIPT - | 21 | 2016-04-13
14 | Compare ACP to CA ICE | CRB + | 7 | 2016-04-20 | OIPT - | 14 | 2016-04-20
15 | Army OIPT | CRB + | 21 | 2016-05-04 | OIPT | 0 | 2016-05-04 | Enter Date
16 | Deliver ASA(FM&C) Approved ACP (FM&C Memo/CAB/Affordability Memo) | CRB + | 31 | 2016-05-14 | OIPT + | 10 | 2016-05-14
17 | OSD OIPT | CRB + | 35 | 2016-05-18 | OIPT + | 14 | 2016-05-18
18 | ASARC | CRB + | 49 | 2016-06-01 | OIPT + | 28 | 2016-06-01
19 | DAB | OIPT + | 63 | 2016-06-15 | OIPT + | 42 | 2016-06-15
The Draft CARD submitted to ASA(ALT)/DASA-CE/CA 180 days prior to the CRB (201 days prior to the Army OIPT) does not require PEO signature
The CARD submitted to ASA(ALT) 128 days prior to the CRB (149 days prior to the Army OIPT) does require PEO signature
DoDI 5000.73 bases dates on the OSD OIPT, these dates are based on the Army OIPT
DoDI 5000.73 requires delivery of the final CARD 21 days prior to the CRB. The final CARD will not be provided until the CRB reviews the recommended ACP
CA - Cost Assessment Directorate of CAPE
ICE - Independent Cost Estimate
CCA - Component Cost Assessment

## MS B RFP Release Rvw ACAT 1 D&C
Draft Army Cost Position Development Timeline Planner (ACAT 1D/C)
DoDI 5000.73 states that the CAPE will meet with representatives from the Service Cost Agency and Program Office no later than 180 calendar days before the scheduled Development RFP Release Decision Point. At this meeting, it will be determined what cost analysis, if any, will be presented at the Decision Point Review and who will be responsible for preparing it. For some programs, the Milestone A ICE will suffice as is or it is updated. In other cases, the cost analysis may be a complete ICE. The DoDI 5000.73 contains timelines developed by the OSD CAPE for submission of documents to support Milestone Reviews and are tied to the OSD OIPT. HQDA and the Program Office must complete the cost analysis and affordability analysis in time to support the Army OIPT. The dates in this timeline planner were developed to be as consistent as possible with the OSD timelines but provide the Army staff sufficient time to complete the required analyses to inform the Army staff at the Army OIPT.
The objective is to complete the draft ACP and Affordability Analysis to support Army OIPT
DASA-CE Darft ACP Review occurs 70 Days after Draft CARD is briefed to the CRBWG
Enter desired Army OIPT Date and the rest of the dates will automatically calculate
ACAT 1C |  | Measured from Army OIPT Date
1 | PM/CRBWG Cost WIPT with CAPE | OIPT - | 180 | 2016-01-05
2 | Draft CARD Submission to ASA(ALT) | OIPT - | 130 | 2016-02-24
3 | CARD Brief to CRB Working Group | OIPT - | 90 | 2016-04-04
4 | CRB Working Group Kick-Off (Draft ACP presented to CRBWG/CA) | OIPT - | 40 | 2016-05-24
5 | Draft ACP Presented to the DASA-CE | OIPT - | 20 | 2016-06-13
6 | Army OIPT | OIPT | 0 | 2016-07-03 | Enter Date
8 | OSD OIPT | OIPT + | 14 | 2016-07-17
9 | ASARC | OIPT + | 28 | 2016-07-31
10 | DAB | OIPT + | 42 | 2016-08-14
The Draft CARD submitted to ASA(ALT)/DASA-CE/CA 120 days prior to the Army OIPT does not require PEO signature
DoDI 5000.73 bases dates on the RFP Release Review Decision date, these dates are based on the Army OIPT
CA - Cost Assessment Directorate of CAPE
ICE - Independent Cost Estimate
CCA - Component Cost Assessment