## Planner
INSTRUCTIONS: fill out section below and then copy & paste the cell range (in the red boxed area) into the body of an email addressed as follows: TO: usarmy.belvoir.hqda-asa-fm.list.dasa-ce-crb-office@army.mil CC: usarmy.pentagon.hqda-asa-alt.list.ara@army.mil
|  | Fields with asterisks * are required to generate a planning timeline | [6 empty] | Non SWP
|  | * Program Name: |  |  | <--Spell out Program Name | per FY2026 NDAA Sec 1804 |  |  | SWP
|  | * Capability Program Executive (CPE): |  |  | <--Spell out CPE Name |  | RDT&E | PROC
|  | * Acquisition Pathway: |  |  | <--Select from list |  | Greater Than or Equal To | Greater Than or Equal To
CY2024 $M
|  | * Event Estimate Support: |  |  | <--Select from list | MDAP (ACAT I) | 1000 | 4500
|  | * ACAT or ACAT Equivalent: |  |  | <--Select from list | Major (ACAT II) | 275 | 1300
|  | * Decision Authority: |  |  | <--Select from list | ACAT III | 125 | 510
|  | THIS DATE INPUT LABEL WILL UPDATE BASED ON INPUTS ABOVE |  |  | <-- enter in mm/dd/yyyy format | ACAT IV | < $ 125 | < $ 510
notes:
|  | Program Management Office Point of Contact: |  |  | <-- enter name & email address | 1. for MCAs, above $ figures are for lifecycle
|  | Estimated RDT&E Costs in CY2024$M for (for period of acquisition pathway): |  |  | <-- enter in CY2024 $M | 2. For MTAs and SWPs, above $ figures are
|  | Fiscal Year Start RDT&E (for period of acquisition pathway): |  |  | <-- enter in yyyy format | generally for the period (5-yr max) of pathway
|  | Fiscal Year End RDT&E for (for period of acquisition pathway): |  |  | <-- enter in yyyy format
|  | Estimated Procurement Costs in CY2024$M (for period of acquisition pathway): |  |  | <-- enter in CY2024 $M | per DoDI 5000.75 (Chg 2 Jan 2020)
|  | Fiscal Year Start PROC (for period of acquisition pathway): |  |  | <-- enter in yyyy format |  | ALL APPNS
|  | Fiscal Year End PROC (for period of acquisition pathway): |  |  | <-- enter in yyyy format |  | Greater Than
|  | Estimated RDT&E Costs in CY2024$M (for full program life cycle): |  |  | <-- enter in CY2024 $M | TY $M
|  | Fiscal Year Start RDT&E (for full program life cycle) |  |  | <-- enter in yyyy format | BCAT I | 250
|  | Fiscal Year End RDT&E (for full program life cycle) |  |  | <-- enter in yyyy format | BCAT II | 50
|  | Estimated Procurement Costs in CY2024$M (for full program life cycle): |  |  | <-- enter in CY2024 $M | BCAT III | < $ 50
|  | Fiscal Year Start PROC (for full program life cycle) |  |  | <-- enter in yyyy format | notes:
|  | Fiscal Year End PROC (for full program life cycle) |  |  | <-- enter in yyyy format | 1. above $ figures are for period of FYDP
|  | Estimated All Appropriations Costs in CY2024$M (for full program life cycle) |  |  | <-- enter in CY2024 $M
|  | Fiscal Year Start ALL APPNS (for full program lifecycle) |  |  | <-- enter in yyyy format
|  | Fiscal Year End ALL APPNS (for full program lifecycle) |  |  | <-- enter in yyyy format
#N/A
Planning Timeline will be updated once CRB Analyst is notified and events are coordinated with ASA(ALT) and PMO (Planner attempts to block off weekends and holiday periods for more realistic planning)
2 | #N/A
3 | #N/A
4 | #N/A
| Event # | Planning Timeline for Cost Product | Measured from DATE INPUT LABEL WILL UPDATE BASED ON INPUTS ABOVE | [8 empty] | Alt measure | Alt Date
5 |  | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2023-12-16 | 2023-12-15
6 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2023-12-17 | 2023-12-18
7 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2023-12-23 | 2023-12-22
8 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2023-12-24 | 2023-12-25
9 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2023-12-30 | 2023-12-29
10 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2023-12-31 | 2024-01-01
11 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-01-06 | 2024-01-05
12 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-01-07 | 2024-01-08
13 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-01-13 | 2024-01-12
14 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-01-14 | 2024-01-15
15 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-01-20 | 2024-01-19
16 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-01-21 | 2024-01-22
17 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-01-27 | 2024-01-26
18 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-01-28 | 2024-01-29
19 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-02-03 | 2024-02-02
20 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-02-04 | 2024-02-05
21 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-02-10 | 2024-02-09
22 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-02-11 | 2024-02-12
23 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-02-17 | 2024-02-16
24 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-02-18 | 2024-02-19
25 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-02-24 | 2024-02-23
26 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-02-25 | 2024-02-26
27 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-03-02 | 2024-03-01
28 | #N/A | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A | #N/A | Weekends | 2024-03-03 | 2024-03-04
33 | #N/A | [12 empty] | Weekends | 2024-03-09 | 2024-03-08
[14 empty] | Weekends | 2024-03-10 | 2024-03-11
[14 empty] | Weekends | 2024-03-16 | 2024-03-15
[14 empty] | Weekends | 2024-03-17 | 2024-03-18
|  | #N/A | [11 empty] | Weekends | 2024-03-23 | 2024-03-22
[14 empty] | Weekends | 2024-03-24 | 2024-03-25
[14 empty] | Weekends | 2024-03-30 | 2024-03-29
|  | FALSE | [11 empty] | Weekends | 2024-03-31 | 2024-04-01
[14 empty] | Weekends | 2024-04-06 | 2024-04-05
[14 empty] | Weekends | 2024-04-07 | 2024-04-08
[14 empty] | Weekends | 2024-04-13 | 2024-04-12
[14 empty] | Weekends | 2024-04-14 | 2024-04-15
[14 empty] | Weekends | 2024-04-20 | 2024-04-19
[14 empty] | Weekends | 2024-04-21 | 2024-04-22
[14 empty] | Weekends | 2024-04-27 | 2024-04-26
[14 empty] | Weekends | 2024-04-28 | 2024-04-29
[14 empty] | Weekends | 2024-05-04 | 2024-05-03
[14 empty] | Weekends | 2024-05-05 | 2024-05-06
[14 empty] | Weekends | 2024-05-11 | 2024-05-10
[14 empty] | Weekends | 2024-05-12 | 2024-05-13
[14 empty] | Weekends | 2024-05-18 | 2024-05-17
[14 empty] | Weekends | 2024-05-19 | 2024-05-20
[14 empty] | Weekends | 2024-05-25 | 2024-05-24
[14 empty] | Weekends | 2024-05-26 | 2024-05-27
[14 empty] | Weekends | 2024-06-01 | 2024-05-31
[14 empty] | Weekends | 2024-06-02 | 2024-06-03
[14 empty] | Weekends | 2024-06-08 | 2024-06-07
[14 empty] | Weekends | 2024-06-09 | 2024-06-10
[14 empty] | Weekends | 2024-06-15 | 2024-06-14
[14 empty] | Weekends | 2024-06-16 | 2024-06-17
[14 empty] | Weekends | 2024-06-22 | 2024-06-21
[14 empty] | Weekends | 2024-06-23 | 2024-06-24
[14 empty] | Weekends | 2024-06-29 | 2024-06-28
[14 empty] | Weekends | 2024-06-30 | 2024-07-01
[14 empty] | Weekends | 2024-07-06 | 2024-07-05
[14 empty] | Weekends | 2024-07-07 | 2024-07-08
[14 empty] | Weekends | 2024-07-13 | 2024-07-12
[14 empty] | Weekends | 2024-07-14 | 2024-07-15
[14 empty] | Weekends | 2024-07-20 | 2024-07-19
[14 empty] | Weekends | 2024-07-21 | 2024-07-22
[14 empty] | Weekends | 2024-07-27 | 2024-07-26
[14 empty] | Weekends | 2024-07-28 | 2024-07-29
[14 empty] | Weekends | 2024-08-03 | 2024-08-02
[14 empty] | Weekends | 2024-08-04 | 2024-08-05
[14 empty] | Weekends | 2024-08-10 | 2024-08-09
[14 empty] | Weekends | 2024-08-11 | 2024-08-12
[14 empty] | Weekends | 2024-08-17 | 2024-08-16
[14 empty] | Weekends | 2024-08-18 | 2024-08-19
[14 empty] | Weekends | 2024-08-24 | 2024-08-23
[14 empty] | Weekends | 2024-08-25 | 2024-08-26
[14 empty] | Weekends | 2024-08-31 | 2024-08-30
[14 empty] | Weekends | 2024-09-01 | 2024-09-02
[14 empty] | Weekends | 2024-09-07 | 2024-09-06
[14 empty] | Weekends | 2024-09-08 | 2024-09-09
[14 empty] | Weekends | 2024-09-14 | 2024-09-13
[14 empty] | Weekends | 2024-09-15 | 2024-09-16
[14 empty] | Weekends | 2024-09-21 | 2024-09-20
[14 empty] | Weekends | 2024-09-22 | 2024-09-23
[14 empty] | Weekends | 2024-09-28 | 2024-09-27
[14 empty] | Weekends | 2024-09-29 | 2024-09-30
[14 empty] | Weekends | 2024-10-05 | 2024-10-04
[14 empty] | Weekends | 2024-10-06 | 2024-10-07
[14 empty] | Weekends | 2024-10-12 | 2024-10-11
[14 empty] | Weekends | 2024-10-13 | 2024-10-14
[14 empty] | Weekends | 2024-10-19 | 2024-10-18
[14 empty] | Weekends | 2024-10-20 | 2024-10-21
[14 empty] | Weekends | 2024-10-26 | 2024-10-25
[14 empty] | Weekends | 2024-10-27 | 2024-10-28
[14 empty] | Weekends | 2024-11-02 | 2024-11-01
[14 empty] | Weekends | 2024-11-03 | 2024-11-04
[14 empty] | Weekends | 2024-11-09 | 2024-11-08
[14 empty] | Weekends | 2024-11-10 | 2024-11-11
[14 empty] | Weekends | 2024-11-16 | 2024-11-15
[14 empty] | Weekends | 2024-11-17 | 2024-11-18
[14 empty] | Weekends | 2024-11-23 | 2024-11-22
[14 empty] | Weekends | 2024-11-24 | 2024-11-25
[14 empty] | Weekends | 2024-11-30 | 2024-11-29
[14 empty] | Weekends | 2024-12-01 | 2024-12-02
[14 empty] | Weekends | 2024-12-07 | 2024-12-06
[14 empty] | Weekends | 2024-12-08 | 2024-12-09
[14 empty] | Weekends | 2024-12-14 | 2024-12-13
[14 empty] | Weekends | 2024-12-15 | 2024-12-16
[14 empty] | Weekends | 2024-12-21 | 2024-12-20
[14 empty] | Weekends | 2024-12-22 | 2024-12-23
[14 empty] | Weekends | 2024-12-28 | 2024-12-27
[14 empty] | Weekends | 2024-12-29 | 2024-12-30
[14 empty] | Weekends | 2025-01-04 | 2025-01-03
[14 empty] | Weekends | 2025-01-05 | 2025-01-06
[14 empty] | Weekends | 2025-01-11 | 2025-01-10
[14 empty] | Weekends | 2025-01-12 | 2025-01-13
[14 empty] | Weekends | 2025-01-18 | 2025-01-17
[14 empty] | Weekends | 2025-01-19 | 2025-01-20
[14 empty] | Weekends | 2025-01-25 | 2025-01-24
[14 empty] | Weekends | 2025-01-26 | 2025-01-27
[14 empty] | Weekends | 2025-02-01 | 2025-01-31
[14 empty] | Weekends | 2025-02-02 | 2025-02-03
[14 empty] | Weekends | 2025-02-08 | 2025-02-07
[14 empty] | Weekends | 2025-02-09 | 2025-02-10
[14 empty] | Weekends | 2025-02-15 | 2025-02-14
[14 empty] | Weekends | 2025-02-16 | 2025-02-17
[14 empty] | Weekends | 2025-02-22 | 2025-02-21
[14 empty] | Weekends | 2025-02-23 | 2025-02-24
[14 empty] | Weekends | 2025-03-01 | 2025-02-28
[14 empty] | Weekends | 2025-03-02 | 2025-03-03
[14 empty] | Weekends | 2025-03-08 | 2025-03-07
[14 empty] | Weekends | 2025-03-09 | 2025-03-10
[14 empty] | Weekends | 2025-03-15 | 2025-03-14
[14 empty] | Weekends | 2025-03-16 | 2025-03-17
[14 empty] | Weekends | 2025-03-22 | 2025-03-21
[14 empty] | Weekends | 2025-03-23 | 2025-03-24
[14 empty] | Weekends | 2025-03-29 | 2025-03-28
[14 empty] | Weekends | 2025-03-30 | 2025-03-31
[14 empty] | Weekends | 2025-04-05 | 2025-04-04
[14 empty] | Weekends | 2025-04-06 | 2025-04-07
[14 empty] | Weekends | 2025-04-12 | 2025-04-11
[14 empty] | Weekends | 2025-04-13 | 2025-04-14
[14 empty] | Weekends | 2025-04-19 | 2025-04-18
[14 empty] | Weekends | 2025-04-20 | 2025-04-21
[14 empty] | Weekends | 2025-04-26 | 2025-04-25
[14 empty] | Weekends | 2025-04-27 | 2025-04-28
[14 empty] | Weekends | 2025-05-03 | 2025-05-02
[14 empty] | Weekends | 2025-05-04 | 2025-05-05
[14 empty] | Weekends | 2025-05-10 | 2025-05-09
[14 empty] | Weekends | 2025-05-11 | 2025-05-12
[14 empty] | Weekends | 2025-05-17 | 2025-05-16
[14 empty] | Weekends | 2025-05-18 | 2025-05-19
[14 empty] | Weekends | 2025-05-24 | 2025-05-23
[14 empty] | Weekends | 2025-05-25 | 2025-05-26
[14 empty] | Weekends | 2025-05-31 | 2025-05-30
[14 empty] | Weekends | 2025-06-01 | 2025-06-02
[14 empty] | Weekends | 2025-06-07 | 2025-06-06
[14 empty] | Weekends | 2025-06-08 | 2025-06-09
[14 empty] | Weekends | 2025-06-14 | 2025-06-13
[14 empty] | Weekends | 2025-06-15 | 2025-06-16
[14 empty] | Weekends | 2025-06-21 | 2025-06-20
[14 empty] | Weekends | 2025-06-22 | 2025-06-23
[14 empty] | Weekends | 2025-06-28 | 2025-06-27
[14 empty] | Weekends | 2025-06-29 | 2025-06-30
[14 empty] | Weekends | 2025-07-05 | 2025-07-04
[14 empty] | Weekends | 2025-07-06 | 2025-07-07
[14 empty] | Weekends | 2025-07-12 | 2025-07-11
[14 empty] | Weekends | 2025-07-13 | 2025-07-14
[14 empty] | Weekends | 2025-07-19 | 2025-07-18
[14 empty] | Weekends | 2025-07-20 | 2025-07-21
[14 empty] | Weekends | 2025-07-26 | 2025-07-25
[14 empty] | Weekends | 2025-07-27 | 2025-07-28
[14 empty] | Weekends | 2025-08-02 | 2025-08-01
[14 empty] | Weekends | 2025-08-03 | 2025-08-04
[14 empty] | Weekends | 2025-08-09 | 2025-08-08
[14 empty] | Weekends | 2025-08-10 | 2025-08-11
[14 empty] | Weekends | 2025-08-16 | 2025-08-15
[14 empty] | Weekends | 2025-08-17 | 2025-08-18
[14 empty] | Weekends | 2025-08-23 | 2025-08-22
[14 empty] | Weekends | 2025-08-24 | 2025-08-25
[14 empty] | Weekends | 2025-08-30 | 2025-08-29
[14 empty] | Weekends | 2025-08-31 | 2025-09-01
[14 empty] | Weekends | 2025-09-06 | 2025-09-05
[14 empty] | Weekends | 2025-09-07 | 2025-09-08
[14 empty] | Weekends | 2025-09-13 | 2025-09-12
[14 empty] | Weekends | 2025-09-14 | 2025-09-15
[14 empty] | Weekends | 2025-09-20 | 2025-09-19
[14 empty] | Weekends | 2025-09-21 | 2025-09-22
[14 empty] | Weekends | 2025-09-27 | 2025-09-26
[14 empty] | Weekends | 2025-09-28 | 2025-09-29
[14 empty] | Weekends | 2025-10-04 | 2025-10-03
[14 empty] | Weekends | 2025-10-05 | 2025-10-06
[14 empty] | Weekends | 2025-10-11 | 2025-10-10
[14 empty] | Weekends | 2025-10-12 | 2025-10-13
[14 empty] | Weekends | 2025-10-18 | 2025-10-17
[14 empty] | Weekends | 2025-10-19 | 2025-10-20
[14 empty] | Weekends | 2025-10-25 | 2025-10-24
[14 empty] | Weekends | 2025-10-26 | 2025-10-27
[14 empty] | Weekends | 2025-11-01 | 2025-10-31
[14 empty] | Weekends | 2025-11-02 | 2025-11-03
[14 empty] | Weekends | 2025-11-08 | 2025-11-07
[14 empty] | Weekends | 2025-11-09 | 2025-11-10
[14 empty] | Weekends | 2025-11-15 | 2025-11-14
[14 empty] | Weekends | 2025-11-16 | 2025-11-17
[14 empty] | Weekends | 2025-11-22 | 2025-11-21
[14 empty] | Weekends | 2025-11-23 | 2025-11-24
[14 empty] | Weekends | 2025-11-29 | 2025-11-28
[14 empty] | Weekends | 2025-11-30 | 2025-12-01
[14 empty] | Weekends | 2025-12-06 | 2025-12-05
[14 empty] | Weekends | 2025-12-07 | 2025-12-08
[14 empty] | Weekends | 2025-12-13 | 2025-12-12
[14 empty] | Weekends | 2025-12-14 | 2025-12-15
[14 empty] | Weekends | 2025-12-20 | 2025-12-19
[14 empty] | Weekends | 2025-12-21 | 2025-12-22
[14 empty] | Weekends | 2025-12-27 | 2025-12-26
[14 empty] | Weekends | 2025-12-28 | 2025-12-29
[14 empty] | Weekends | 2026-01-03 | 2026-01-02
[14 empty] | Weekends | 2026-01-04 | 2026-01-05
[14 empty] | Weekends | 2026-01-10 | 2026-01-09
[14 empty] | Weekends | 2026-01-11 | 2026-01-12
[14 empty] | Weekends | 2026-01-17 | 2026-01-16
[14 empty] | Weekends | 2026-01-18 | 2026-01-19
[14 empty] | Weekends | 2026-01-24 | 2026-01-23
[14 empty] | Weekends | 2026-01-25 | 2026-01-26
[14 empty] | Weekends | 2026-01-31 | 2026-01-30
[14 empty] | Weekends | 2026-02-01 | 2026-02-02
[14 empty] | Weekends | 2026-02-07 | 2026-02-06
[14 empty] | Weekends | 2026-02-08 | 2026-02-09
[14 empty] | Weekends | 2026-02-14 | 2026-02-13
[14 empty] | Weekends | 2026-02-15 | 2026-02-16
[14 empty] | Weekends | 2026-02-21 | 2026-02-20
[14 empty] | Weekends | 2026-02-22 | 2026-02-23
[14 empty] | Weekends | 2026-02-28 | 2026-02-27
[14 empty] | Weekends | 2026-03-01 | 2026-03-02
[14 empty] | Weekends | 2026-03-07 | 2026-03-06
[14 empty] | Weekends | 2026-03-08 | 2026-03-09
[14 empty] | Weekends | 2026-03-14 | 2026-03-13
[14 empty] | Weekends | 2026-03-15 | 2026-03-16
[14 empty] | Weekends | 2026-03-21 | 2026-03-20
[14 empty] | Weekends | 2026-03-22 | 2026-03-23
[14 empty] | Weekends | 2026-03-28 | 2026-03-27
[14 empty] | Weekends | 2026-03-29 | 2026-03-30
[14 empty] | Weekends | 2026-04-04 | 2026-04-03
[14 empty] | Weekends | 2026-04-05 | 2026-04-06
[14 empty] | Weekends | 2026-04-11 | 2026-04-10
[14 empty] | Weekends | 2026-04-12 | 2026-04-13
[14 empty] | Weekends | 2026-04-18 | 2026-04-17
[14 empty] | Weekends | 2026-04-19 | 2026-04-20
[14 empty] | Weekends | 2026-04-25 | 2026-04-24
[14 empty] | Weekends | 2026-04-26 | 2026-04-27
[14 empty] | Weekends | 2026-05-02 | 2026-05-01
[14 empty] | Weekends | 2026-05-03 | 2026-05-04
[14 empty] | Weekends | 2026-05-09 | 2026-05-08
[14 empty] | Weekends | 2026-05-10 | 2026-05-11
[14 empty] | Weekends | 2026-05-16 | 2026-05-15
[14 empty] | Weekends | 2026-05-17 | 2026-05-18
[14 empty] | Weekends | 2026-05-23 | 2026-05-22
[14 empty] | Weekends | 2026-05-24 | 2026-05-25
[14 empty] | Weekends | 2026-05-30 | 2026-05-29
[14 empty] | Weekends | 2026-05-31 | 2026-06-01
[14 empty] | Weekends | 2026-06-06 | 2026-06-05
[14 empty] | Weekends | 2026-06-07 | 2026-06-08
[14 empty] | Weekends | 2026-06-13 | 2026-06-12
[14 empty] | Weekends | 2026-06-14 | 2026-06-15
[14 empty] | Weekends | 2026-06-20 | 2026-06-19
[14 empty] | Weekends | 2026-06-21 | 2026-06-22
[14 empty] | Weekends | 2026-06-27 | 2026-06-26
[14 empty] | Weekends | 2026-06-28 | 2026-06-29
[14 empty] | Weekends | 2026-07-04 | 2026-07-03
[14 empty] | Weekends | 2026-07-05 | 2026-07-06
[14 empty] | Weekends | 2026-07-11 | 2026-07-10
[14 empty] | Weekends | 2026-07-12 | 2026-07-13
[14 empty] | Weekends | 2026-07-18 | 2026-07-17
[14 empty] | Weekends | 2026-07-19 | 2026-07-20
[14 empty] | Weekends | 2026-07-25 | 2026-07-24
[14 empty] | Weekends | 2026-07-26 | 2026-07-27
[14 empty] | Weekends | 2026-08-01 | 2026-07-31
[14 empty] | Weekends | 2026-08-02 | 2026-08-03
[14 empty] | Weekends | 2026-08-08 | 2026-08-07
[14 empty] | Weekends | 2026-08-09 | 2026-08-10
[14 empty] | Weekends | 2026-08-15 | 2026-08-14
[14 empty] | Weekends | 2026-08-16 | 2026-08-17
[14 empty] | Weekends | 2026-08-22 | 2026-08-21
[14 empty] | Weekends | 2026-08-23 | 2026-08-24
[14 empty] | Weekends | 2026-08-29 | 2026-08-28
[14 empty] | Weekends | 2026-08-30 | 2026-08-31
[14 empty] | Weekends | 2026-09-05 | 2026-09-04
[14 empty] | Weekends | 2026-09-06 | 2026-09-07
[14 empty] | Weekends | 2026-09-12 | 2026-09-11
[14 empty] | Weekends | 2026-09-13 | 2026-09-14
[14 empty] | Weekends | 2026-09-19 | 2026-09-18
[14 empty] | Weekends | 2026-09-20 | 2026-09-21
[14 empty] | Weekends | 2026-09-26 | 2026-09-25
[14 empty] | Weekends | 2026-09-27 | 2026-09-28
[14 empty] | Weekends | 2026-10-03 | 2026-10-02
[14 empty] | Weekends | 2026-10-04 | 2026-10-05
[14 empty] | Weekends | 2026-10-10 | 2026-10-09
[14 empty] | Weekends | 2026-10-11 | 2026-10-12
[14 empty] | Weekends | 2026-10-17 | 2026-10-16
[14 empty] | Weekends | 2026-10-18 | 2026-10-19
[14 empty] | Weekends | 2026-10-24 | 2026-10-23
[14 empty] | Weekends | 2026-10-25 | 2026-10-26
[14 empty] | Weekends | 2026-10-31 | 2026-10-30
[14 empty] | Weekends | 2026-11-01 | 2026-11-02
[14 empty] | Weekends | 2026-11-07 | 2026-11-06
[14 empty] | Weekends | 2026-11-08 | 2026-11-09
[14 empty] | Weekends | 2026-11-14 | 2026-11-13
[14 empty] | Weekends | 2026-11-15 | 2026-11-16
[14 empty] | Weekends | 2026-11-21 | 2026-11-20
[14 empty] | Weekends | 2026-11-22 | 2026-11-23
[14 empty] | Weekends | 2026-11-28 | 2026-11-27
[14 empty] | Weekends | 2026-11-29 | 2026-11-30
[14 empty] | Weekends | 2026-12-05 | 2026-12-04
[14 empty] | Weekends | 2026-12-06 | 2026-12-07
[14 empty] | Weekends | 2026-12-12 | 2026-12-11
[14 empty] | Weekends | 2026-12-13 | 2026-12-14
[14 empty] | Weekends | 2026-12-19 | 2026-12-18
[14 empty] | Weekends | 2026-12-20 | 2026-12-21
[14 empty] | Weekends | 2026-12-26 | 2026-12-25
[14 empty] | Weekends | 2026-12-27 | 2026-12-28
[14 empty] | Weekends | 2027-01-02 | 2027-01-01
[14 empty] | Weekends | 2027-01-03 | 2027-01-04
[14 empty] | Weekends | 2027-01-09 | 2027-01-08
[14 empty] | Weekends | 2027-01-10 | 2027-01-11
[14 empty] | Weekends | 2027-01-16 | 2027-01-15
[14 empty] | Weekends | 2027-01-17 | 2027-01-18
[14 empty] | Weekends | 2027-01-23 | 2027-01-22
[14 empty] | Weekends | 2027-01-24 | 2027-01-25
[14 empty] | Weekends | 2027-01-30 | 2027-01-29
[14 empty] | Weekends | 2027-01-31 | 2027-02-01
[14 empty] | Weekends | 2027-02-06 | 2027-02-05
[14 empty] | Weekends | 2027-02-07 | 2027-02-08
[14 empty] | Weekends | 2027-02-13 | 2027-02-12
[14 empty] | Weekends | 2027-02-14 | 2027-02-15
[14 empty] | Weekends | 2027-02-20 | 2027-02-19
[14 empty] | Weekends | 2027-02-21 | 2027-02-22
[14 empty] | Weekends | 2027-02-27 | 2027-02-26
[14 empty] | Weekends | 2027-02-28 | 2027-03-01
[14 empty] | Weekends | 2027-03-06 | 2027-03-05
[14 empty] | Weekends | 2027-03-07 | 2027-03-08
[14 empty] | Weekends | 2027-03-13 | 2027-03-12
[14 empty] | Weekends | 2027-03-14 | 2027-03-15
[14 empty] | Weekends | 2027-03-20 | 2027-03-19
[14 empty] | Weekends | 2027-03-21 | 2027-03-22
[14 empty] | Weekends | 2027-03-27 | 2027-03-26
[14 empty] | Weekends | 2027-03-28 | 2027-03-29
[14 empty] | Weekends | 2027-04-03 | 2027-04-02
[14 empty] | Weekends | 2027-04-04 | 2027-04-05
[14 empty] | Weekends | 2027-04-10 | 2027-04-09
[14 empty] | Weekends | 2027-04-11 | 2027-04-12
[14 empty] | Weekends | 2027-04-17 | 2027-04-16
[14 empty] | Weekends | 2027-04-18 | 2027-04-19
[14 empty] | Weekends | 2027-04-24 | 2027-04-23
[14 empty] | Weekends | 2027-04-25 | 2027-04-26
[14 empty] | Weekends | 2027-05-01 | 2027-04-30
[14 empty] | Weekends | 2027-05-02 | 2027-05-03
[14 empty] | Weekends | 2027-05-08 | 2027-05-07
[14 empty] | Weekends | 2027-05-09 | 2027-05-10
[14 empty] | Weekends | 2027-05-15 | 2027-05-14
[14 empty] | Weekends | 2027-05-16 | 2027-05-17
[14 empty] | Weekends | 2027-05-22 | 2027-05-21
[14 empty] | Weekends | 2027-05-23 | 2027-05-24
[14 empty] | Weekends | 2027-05-29 | 2027-05-28
[14 empty] | Weekends | 2027-05-30 | 2027-05-31
[14 empty] | Weekends | 2027-06-05 | 2027-06-04
[14 empty] | Weekends | 2027-06-06 | 2027-06-07
[14 empty] | Weekends | 2027-06-12 | 2027-06-11
[14 empty] | Weekends | 2027-06-13 | 2027-06-14
[14 empty] | Weekends | 2027-06-19 | 2027-06-18
[14 empty] | Weekends | 2027-06-20 | 2027-06-21
[14 empty] | Weekends | 2027-06-26 | 2027-06-25
[14 empty] | Weekends | 2027-06-27 | 2027-06-28
[14 empty] | Weekends | 2027-07-03 | 2027-07-02
[14 empty] | Weekends | 2027-07-04 | 2027-07-05
[14 empty] | Weekends | 2027-07-10 | 2027-07-09
[14 empty] | Weekends | 2027-07-11 | 2027-07-12
[14 empty] | Weekends | 2027-07-17 | 2027-07-16
[14 empty] | Weekends | 2027-07-18 | 2027-07-19
[14 empty] | Weekends | 2027-07-24 | 2027-07-23
[14 empty] | Weekends | 2027-07-25 | 2027-07-26
[14 empty] | Weekends | 2027-07-31 | 2027-07-30
[14 empty] | Weekends | 2027-08-01 | 2027-08-02
[14 empty] | Weekends | 2027-08-07 | 2027-08-06
[14 empty] | Weekends | 2027-08-08 | 2027-08-09
[14 empty] | Weekends | 2027-08-14 | 2027-08-13
[14 empty] | Weekends | 2027-08-15 | 2027-08-16
[14 empty] | Weekends | 2027-08-21 | 2027-08-20
[14 empty] | Weekends | 2027-08-22 | 2027-08-23
[14 empty] | Weekends | 2027-08-28 | 2027-08-27
[14 empty] | Weekends | 2027-08-29 | 2027-08-30
[14 empty] | Weekends | 2027-09-04 | 2027-09-03
[14 empty] | Weekends | 2027-09-05 | 2027-09-06
[14 empty] | Weekends | 2027-09-11 | 2027-09-10
[14 empty] | Weekends | 2027-09-12 | 2027-09-13
[14 empty] | Weekends | 2027-09-18 | 2027-09-17
[14 empty] | Weekends | 2027-09-19 | 2027-09-20
[14 empty] | Weekends | 2027-09-25 | 2027-09-24
[14 empty] | Weekends | 2027-09-26 | 2027-09-27
[14 empty] | Weekends | 2027-10-02 | 2027-10-01
[14 empty] | Weekends | 2027-10-03 | 2027-10-04
[14 empty] | Weekends | 2027-10-09 | 2027-10-08
[14 empty] | Weekends | 2027-10-10 | 2027-10-11
[14 empty] | Weekends | 2027-10-16 | 2027-10-15
[14 empty] | Weekends | 2027-10-17 | 2027-10-18
[14 empty] | Weekends | 2027-10-23 | 2027-10-22
[14 empty] | Weekends | 2027-10-24 | 2027-10-25
[14 empty] | Weekends | 2027-10-30 | 2027-10-29
[14 empty] | Weekends | 2027-10-31 | 2027-11-01
[14 empty] | Weekends | 2027-11-06 | 2027-11-05
[14 empty] | Weekends | 2027-11-07 | 2027-11-08
[14 empty] | Weekends | 2027-11-13 | 2027-11-12
[14 empty] | Weekends | 2027-11-14 | 2027-11-15
[14 empty] | Weekends | 2027-11-20 | 2027-11-19
[14 empty] | Weekends | 2027-11-21 | 2027-11-22
[14 empty] | Weekends | 2027-11-27 | 2027-11-26
[14 empty] | Weekends | 2027-11-28 | 2027-11-29
[14 empty] | Weekends | 2027-12-04 | 2027-12-03
[14 empty] | Weekends | 2027-12-05 | 2027-12-06
[14 empty] | Weekends | 2027-12-11 | 2027-12-10
[14 empty] | Weekends | 2027-12-12 | 2027-12-13
[14 empty] | Weekends | 2027-12-18 | 2027-12-17
[14 empty] | Weekends | 2027-12-19 | 2027-12-20
[14 empty] | Weekends | 2027-12-25 | 2027-12-24
[14 empty] | Weekends | 2027-12-26 | 2027-12-27
[14 empty] | Weekends | 2028-01-01 | 2027-12-31
[14 empty] | Weekends | 2028-01-02 | 2028-01-03
[14 empty] | Weekends | 2028-01-08 | 2028-01-07
[14 empty] | Weekends | 2028-01-09 | 2028-01-10
[14 empty] | Weekends | 2028-01-15 | 2028-01-14
[14 empty] | Weekends | 2028-01-16 | 2028-01-17
[14 empty] | Weekends | 2028-01-22 | 2028-01-21
[14 empty] | Weekends | 2028-01-23 | 2028-01-24
[14 empty] | Weekends | 2028-01-29 | 2028-01-28
[14 empty] | Weekends | 2028-01-30 | 2028-01-31
[14 empty] | Weekends | 2028-02-05 | 2028-02-04
[14 empty] | Weekends | 2028-02-06 | 2028-02-07
[14 empty] | Weekends | 2028-02-12 | 2028-02-11
[14 empty] | Weekends | 2028-02-13 | 2028-02-14
[14 empty] | Weekends | 2028-02-19 | 2028-02-18
[14 empty] | Weekends | 2028-02-20 | 2028-02-21
[14 empty] | Weekends | 2028-02-26 | 2028-02-25
[14 empty] | Weekends | 2028-02-27 | 2028-02-28
[14 empty] | Weekends | 2028-03-04 | 2028-03-03
[14 empty] | Weekends | 2028-03-05 | 2028-03-06
[14 empty] | Weekends | 2028-03-11 | 2028-03-10
[14 empty] | Weekends | 2028-03-12 | 2028-03-13
[14 empty] | Weekends | 2028-03-18 | 2028-03-17
[14 empty] | Weekends | 2028-03-19 | 2028-03-20
[14 empty] | Weekends | 2028-03-25 | 2028-03-24
[14 empty] | Weekends | 2028-03-26 | 2028-03-27
[14 empty] | Weekends | 2028-04-01 | 2028-03-31
[14 empty] | Weekends | 2028-04-02 | 2028-04-03
[14 empty] | Weekends | 2028-04-08 | 2028-04-07
[14 empty] | Weekends | 2028-04-09 | 2028-04-10
[14 empty] | Weekends | 2028-04-15 | 2028-04-14
[14 empty] | Weekends | 2028-04-16 | 2028-04-17
[14 empty] | Weekends | 2028-04-22 | 2028-04-21
[14 empty] | Weekends | 2028-04-23 | 2028-04-24
[14 empty] | Weekends | 2028-04-29 | 2028-04-28
[14 empty] | Weekends | 2028-04-30 | 2028-05-01
[14 empty] | Weekends | 2028-05-06 | 2028-05-05
[14 empty] | Weekends | 2028-05-07 | 2028-05-08
[14 empty] | Weekends | 2028-05-13 | 2028-05-12
[14 empty] | Weekends | 2028-05-14 | 2028-05-15
[14 empty] | Weekends | 2028-05-20 | 2028-05-19
[14 empty] | Weekends | 2028-05-21 | 2028-05-22
[14 empty] | Weekends | 2028-05-27 | 2028-05-26
[14 empty] | Weekends | 2028-05-28 | 2028-05-29
[14 empty] | Weekends | 2028-06-03 | 2028-06-02
[14 empty] | Weekends | 2028-06-04 | 2028-06-05
[14 empty] | Weekends | 2028-06-10 | 2028-06-09
[14 empty] | Weekends | 2028-06-11 | 2028-06-12
[14 empty] | Weekends | 2028-06-17 | 2028-06-16
[14 empty] | Weekends | 2028-06-18 | 2028-06-19
[14 empty] | Weekends | 2028-06-24 | 2028-06-23
[14 empty] | Weekends | 2028-06-25 | 2028-06-26
[14 empty] | Weekends | 2028-07-01 | 2028-06-30
[14 empty] | Weekends | 2028-07-02 | 2028-07-03
[14 empty] | Weekends | 2028-07-08 | 2028-07-07
[14 empty] | Weekends | 2028-07-09 | 2028-07-10
[14 empty] | Weekends | 2028-07-15 | 2028-07-14
[14 empty] | Weekends | 2028-07-16 | 2028-07-17
[14 empty] | Weekends | 2028-07-22 | 2028-07-21
[14 empty] | Weekends | 2028-07-23 | 2028-07-24
[14 empty] | Weekends | 2028-07-29 | 2028-07-28
[14 empty] | Weekends | 2028-07-30 | 2028-07-31
[14 empty] | Weekends | 2028-08-05 | 2028-08-04
[14 empty] | Weekends | 2028-08-06 | 2028-08-07
[14 empty] | Weekends | 2028-08-12 | 2028-08-11
[14 empty] | Weekends | 2028-08-13 | 2028-08-14
[14 empty] | Weekends | 2028-08-19 | 2028-08-18
[14 empty] | Weekends | 2028-08-20 | 2028-08-21
[14 empty] | Weekends | 2028-08-26 | 2028-08-25
[14 empty] | Weekends | 2028-08-27 | 2028-08-28
[14 empty] | Weekends | 2028-09-02 | 2028-09-01
[14 empty] | Weekends | 2028-09-03 | 2028-09-04
[14 empty] | Weekends | 2028-09-09 | 2028-09-08
[14 empty] | Weekends | 2028-09-10 | 2028-09-11
[14 empty] | Weekends | 2028-09-16 | 2028-09-15
[14 empty] | Weekends | 2028-09-17 | 2028-09-18
[14 empty] | Weekends | 2028-09-23 | 2028-09-22
[14 empty] | Weekends | 2028-09-24 | 2028-09-25
[14 empty] | Weekends | 2028-09-30 | 2028-09-29
[14 empty] | Weekends | 2028-10-01 | 2028-10-02
[14 empty] | Weekends | 2028-10-07 | 2028-10-06
[14 empty] | Weekends | 2028-10-08 | 2028-10-09
[14 empty] | Weekends | 2028-10-14 | 2028-10-13
[14 empty] | Weekends | 2028-10-15 | 2028-10-16
[14 empty] | Weekends | 2028-10-21 | 2028-10-20
[14 empty] | Weekends | 2028-10-22 | 2028-10-23
[14 empty] | Weekends | 2028-10-28 | 2028-10-27
[14 empty] | Weekends | 2028-10-29 | 2028-10-30
[14 empty] | Weekends | 2028-11-04 | 2028-11-03
[14 empty] | Weekends | 2028-11-05 | 2028-11-06
[14 empty] | Weekends | 2028-11-11 | 2028-11-10
[14 empty] | Weekends | 2028-11-12 | 2028-11-13
[14 empty] | Weekends | 2028-11-18 | 2028-11-17
[14 empty] | Weekends | 2028-11-19 | 2028-11-20
[14 empty] | Weekends | 2028-11-25 | 2028-11-24
[14 empty] | Weekends | 2028-11-26 | 2028-11-27
[14 empty] | Weekends | 2028-12-02 | 2028-12-01
[14 empty] | Weekends | 2028-12-03 | 2028-12-04
[14 empty] | Weekends | 2028-12-09 | 2028-12-08
[14 empty] | Weekends | 2028-12-10 | 2028-12-11
[14 empty] | Weekends | 2028-12-16 | 2028-12-15
[14 empty] | Weekends | 2028-12-17 | 2028-12-18
[14 empty] | Weekends | 2028-12-23 | 2028-12-22
[14 empty] | Weekends | 2028-12-24 | 2028-12-25
[14 empty] | Weekends | 2028-12-30 | 2028-12-29
[14 empty] | Weekends | 2028-12-31 | 2029-01-01
[14 empty] | Weekends | 2029-01-06 | 2029-01-05
[14 empty] | Weekends | 2029-01-07 | 2029-01-08
[14 empty] | Weekends | 2029-01-13 | 2029-01-12
[14 empty] | Weekends | 2029-01-14 | 2029-01-15
[14 empty] | Weekends | 2029-01-20 | 2029-01-19
[14 empty] | Weekends | 2029-01-21 | 2029-01-22
[14 empty] | Weekends | 2029-01-27 | 2029-01-26
[14 empty] | Weekends | 2029-01-28 | 2029-01-29
[14 empty] | Weekends | 2029-02-03 | 2029-02-02
[14 empty] | Weekends | 2029-02-04 | 2029-02-05
[14 empty] | Weekends | 2029-02-10 | 2029-02-09
[14 empty] | Weekends | 2029-02-11 | 2029-02-12
[14 empty] | Weekends | 2029-02-17 | 2029-02-16
[14 empty] | Weekends | 2029-02-18 | 2029-02-19
[14 empty] | Weekends | 2029-02-24 | 2029-02-23
[14 empty] | Weekends | 2029-02-25 | 2029-02-26
[14 empty] | Weekends | 2029-03-03 | 2029-03-02
[14 empty] | Weekends | 2029-03-04 | 2029-03-05
[14 empty] | Weekends | 2029-03-10 | 2029-03-09
[14 empty] | Weekends | 2029-03-11 | 2029-03-12
[14 empty] | Weekends | 2029-03-17 | 2029-03-16
[14 empty] | Weekends | 2029-03-18 | 2029-03-19
[14 empty] | Weekends | 2029-03-24 | 2029-03-23
[14 empty] | Weekends | 2029-03-25 | 2029-03-26
[14 empty] | Weekends | 2029-03-31 | 2029-03-30
[14 empty] | Weekends | 2029-04-01 | 2029-04-02
[14 empty] | Weekends | 2029-04-07 | 2029-04-06
[14 empty] | Weekends | 2029-04-08 | 2029-04-09
[14 empty] | Weekends | 2029-04-14 | 2029-04-13
[14 empty] | Weekends | 2029-04-15 | 2029-04-16
[14 empty] | Weekends | 2029-04-21 | 2029-04-20
[14 empty] | Weekends | 2029-04-22 | 2029-04-23
[14 empty] | Weekends | 2029-04-28 | 2029-04-27
[14 empty] | Weekends | 2029-04-29 | 2029-04-30
[14 empty] | Weekends | 2029-05-05 | 2029-05-04
[14 empty] | Weekends | 2029-05-06 | 2029-05-07
[14 empty] | Weekends | 2029-05-12 | 2029-05-11
[14 empty] | Weekends | 2029-05-13 | 2029-05-14
[14 empty] | Weekends | 2029-05-19 | 2029-05-18
[14 empty] | Weekends | 2029-05-20 | 2029-05-21
[14 empty] | Weekends | 2029-05-26 | 2029-05-25
[14 empty] | Weekends | 2029-05-27 | 2029-05-28
[14 empty] | Weekends | 2029-06-02 | 2029-06-01
[14 empty] | Weekends | 2029-06-03 | 2029-06-04
[14 empty] | Weekends | 2029-06-09 | 2029-06-08
[14 empty] | Weekends | 2029-06-10 | 2029-06-11
[14 empty] | Weekends | 2029-06-16 | 2029-06-15
[14 empty] | Weekends | 2029-06-17 | 2029-06-18
[14 empty] | Weekends | 2029-06-23 | 2029-06-22
[14 empty] | Weekends | 2029-06-24 | 2029-06-25
[14 empty] | Weekends | 2029-06-30 | 2029-06-29
[14 empty] | Weekends | 2029-07-01 | 2029-07-02
[14 empty] | Weekends | 2029-07-07 | 2029-07-06
[14 empty] | Weekends | 2029-07-08 | 2029-07-09
[14 empty] | Weekends | 2029-07-14 | 2029-07-13
[14 empty] | Weekends | 2029-07-15 | 2029-07-16
[14 empty] | Weekends | 2029-07-21 | 2029-07-20
[14 empty] | Weekends | 2029-07-22 | 2029-07-23
[14 empty] | Weekends | 2029-07-28 | 2029-07-27
[14 empty] | Weekends | 2029-07-29 | 2029-07-30
[14 empty] | Weekends | 2029-08-04 | 2029-08-03
[14 empty] | Weekends | 2029-08-05 | 2029-08-06
[14 empty] | Weekends | 2029-08-11 | 2029-08-10
[14 empty] | Weekends | 2029-08-12 | 2029-08-13
[14 empty] | Weekends | 2029-08-18 | 2029-08-17
[14 empty] | Weekends | 2029-08-19 | 2029-08-20
[14 empty] | Weekends | 2029-08-25 | 2029-08-24
[14 empty] | Weekends | 2029-08-26 | 2029-08-27
[14 empty] | Weekends | 2029-09-01 | 2029-08-31
[14 empty] | Weekends | 2029-09-02 | 2029-09-03
[14 empty] | Weekends | 2029-09-08 | 2029-09-07
[14 empty] | Weekends | 2029-09-09 | 2029-09-10
[14 empty] | Weekends | 2029-09-15 | 2029-09-14
[14 empty] | Weekends | 2029-09-16 | 2029-09-17
[14 empty] | Weekends | 2029-09-22 | 2029-09-21
[14 empty] | Weekends | 2029-09-23 | 2029-09-24
[14 empty] | Weekends | 2029-09-29 | 2029-09-28
[14 empty] | Weekends | 2029-09-30 | 2029-10-01
[14 empty] | Weekends | 2029-10-06 | 2029-10-05
[14 empty] | Weekends | 2029-10-07 | 2029-10-08
[14 empty] | Weekends | 2029-10-13 | 2029-10-12
[14 empty] | Weekends | 2029-10-14 | 2029-10-15
[14 empty] | Weekends | 2029-10-20 | 2029-10-19
[14 empty] | Weekends | 2029-10-21 | 2029-10-22
[14 empty] | Weekends | 2029-10-27 | 2029-10-26
[14 empty] | Weekends | 2029-10-28 | 2029-10-29
[14 empty] | Weekends | 2029-11-03 | 2029-11-02
[14 empty] | Weekends | 2029-11-04 | 2029-11-05
[14 empty] | Weekends | 2029-11-10 | 2029-11-09
[14 empty] | Weekends | 2029-11-11 | 2029-11-12
[14 empty] | Weekends | 2029-11-17 | 2029-11-16
[14 empty] | Weekends | 2029-11-18 | 2029-11-19
[14 empty] | Weekends | 2029-11-24 | 2029-11-23
[14 empty] | Weekends | 2029-11-25 | 2029-11-26
[14 empty] | Weekends | 2029-12-01 | 2029-11-30
[14 empty] | Weekends | 2029-12-02 | 2029-12-03
[14 empty] | Weekends | 2029-12-08 | 2029-12-07
[14 empty] | Weekends | 2029-12-09 | 2029-12-10
[14 empty] | Weekends | 2029-12-15 | 2029-12-14
[14 empty] | Weekends | 2029-12-16 | 2029-12-17
[14 empty] | Weekends | 2029-12-22 | 2029-12-21
[14 empty] | Weekends | 2029-12-23 | 2029-12-24
[14 empty] | Weekends | 2029-12-29 | 2029-12-28
[14 empty] | Weekends | 2029-12-30 | 2029-12-31
[14 empty] | Weekends | 2030-01-05 | 2030-01-04
[14 empty] | Weekends | 2030-01-06 | 2030-01-07
[14 empty] | Weekends | 2030-01-12 | 2030-01-11
[14 empty] | Weekends | 2030-01-13 | 2030-01-14
[14 empty] | Weekends | 2030-01-19 | 2030-01-18
[14 empty] | Weekends | 2030-01-20 | 2030-01-21
[14 empty] | Weekends | 2030-01-26 | 2030-01-25
[14 empty] | Weekends | 2030-01-27 | 2030-01-28
[14 empty] | Weekends | 2030-02-02 | 2030-02-01
[14 empty] | Weekends | 2030-02-03 | 2030-02-04
[14 empty] | Weekends | 2030-02-09 | 2030-02-08
[14 empty] | Weekends | 2030-02-10 | 2030-02-11
[14 empty] | Weekends | 2030-02-16 | 2030-02-15
[14 empty] | Weekends | 2030-02-17 | 2030-02-18
[14 empty] | Weekends | 2030-02-23 | 2030-02-22
[14 empty] | Weekends | 2030-02-24 | 2030-02-25
[14 empty] | Weekends | 2030-03-02 | 2030-03-01
[14 empty] | Weekends | 2030-03-03 | 2030-03-04
[14 empty] | Weekends | 2030-03-09 | 2030-03-08
[14 empty] | Weekends | 2030-03-10 | 2030-03-11
[14 empty] | Weekends | 2030-03-16 | 2030-03-15
[14 empty] | Weekends | 2030-03-17 | 2030-03-18
[14 empty] | Weekends | 2030-03-23 | 2030-03-22
[14 empty] | Weekends | 2030-03-24 | 2030-03-25
[14 empty] | Weekends | 2030-03-30 | 2030-03-29
[14 empty] | Weekends | 2030-03-31 | 2030-04-01
[14 empty] | Weekends | 2030-04-06 | 2030-04-05
[14 empty] | Weekends | 2030-04-07 | 2030-04-08
[14 empty] | Weekends | 2030-04-13 | 2030-04-12
[14 empty] | Weekends | 2030-04-14 | 2030-04-15
[14 empty] | Weekends | 2030-04-20 | 2030-04-19
[14 empty] | Weekends | 2030-04-21 | 2030-04-22
[14 empty] | Weekends | 2030-04-27 | 2030-04-26
[14 empty] | Weekends | 2030-04-28 | 2030-04-29
[14 empty] | Weekends | 2030-05-04 | 2030-05-03
[14 empty] | Weekends | 2030-05-05 | 2030-05-06
[14 empty] | Weekends | 2030-05-11 | 2030-05-10
[14 empty] | Weekends | 2030-05-12 | 2030-05-13
[14 empty] | Weekends | 2030-05-18 | 2030-05-17
[14 empty] | Weekends | 2030-05-19 | 2030-05-20
[14 empty] | Weekends | 2030-05-25 | 2030-05-24
[14 empty] | Weekends | 2030-05-26 | 2030-05-27
[14 empty] | Weekends | 2030-06-01 | 2030-05-31
[14 empty] | Weekends | 2030-06-02 | 2030-06-03
[14 empty] | Weekends | 2030-06-08 | 2030-06-07
[14 empty] | Weekends | 2030-06-09 | 2030-06-10
[14 empty] | Weekends | 2030-06-15 | 2030-06-14
[14 empty] | Weekends | 2030-06-16 | 2030-06-17
[14 empty] | Weekends | 2030-06-22 | 2030-06-21
[14 empty] | Weekends | 2030-06-23 | 2030-06-24
[14 empty] | Weekends | 2030-06-29 | 2030-06-28
[14 empty] | Weekends | 2030-06-30 | 2030-07-01
[14 empty] | Weekends | 2030-07-06 | 2030-07-05
[14 empty] | Weekends | 2030-07-07 | 2030-07-08
[14 empty] | Weekends | 2030-07-13 | 2030-07-12
[14 empty] | Weekends | 2030-07-14 | 2030-07-15
[14 empty] | Weekends | 2030-07-20 | 2030-07-19
[14 empty] | Weekends | 2030-07-21 | 2030-07-22
[14 empty] | Weekends | 2030-07-27 | 2030-07-26
[14 empty] | Weekends | 2030-07-28 | 2030-07-29
[14 empty] | Weekends | 2030-08-03 | 2030-08-02
[14 empty] | Weekends | 2030-08-04 | 2030-08-05
[14 empty] | Weekends | 2030-08-10 | 2030-08-09
[14 empty] | Weekends | 2030-08-11 | 2030-08-12
[14 empty] | Weekends | 2030-08-17 | 2030-08-16
[14 empty] | Weekends | 2030-08-18 | 2030-08-19
[14 empty] | Weekends | 2030-08-24 | 2030-08-23
[14 empty] | Weekends | 2030-08-25 | 2030-08-26
[14 empty] | Weekends | 2030-08-31 | 2030-08-30
[14 empty] | Weekends | 2030-09-01 | 2030-09-02
[14 empty] | Weekends | 2030-09-07 | 2030-09-06
[14 empty] | Weekends | 2030-09-08 | 2030-09-09
[14 empty] | Weekends | 2030-09-14 | 2030-09-13
[14 empty] | Weekends | 2030-09-15 | 2030-09-16
[14 empty] | Weekends | 2030-09-21 | 2030-09-20
[14 empty] | Weekends | 2030-09-22 | 2030-09-23
[14 empty] | Weekends | 2030-09-28 | 2030-09-27
[14 empty] | Weekends | 2030-09-29 | 2030-09-30
[14 empty] | Weekends | 2030-10-05 | 2030-10-04
[14 empty] | Weekends | 2030-10-06 | 2030-10-07
[14 empty] | Weekends | 2030-10-12 | 2030-10-11
[14 empty] | Weekends | 2030-10-13 | 2030-10-14
[14 empty] | Weekends | 2030-10-19 | 2030-10-18
[14 empty] | Weekends | 2030-10-20 | 2030-10-21
[14 empty] | Weekends | 2030-10-26 | 2030-10-25
[14 empty] | Weekends | 2030-10-27 | 2030-10-28
[14 empty] | Weekends | 2030-11-02 | 2030-11-01
[14 empty] | Weekends | 2030-11-03 | 2030-11-04
[14 empty] | Weekends | 2030-11-09 | 2030-11-08
[14 empty] | Weekends | 2030-11-10 | 2030-11-11
[14 empty] | Weekends | 2030-11-16 | 2030-11-15
[14 empty] | Weekends | 2030-11-17 | 2030-11-18
[14 empty] | Weekends | 2030-11-23 | 2030-11-22
[14 empty] | Weekends | 2030-11-24 | 2030-11-25
[14 empty] | Weekends | 2030-11-30 | 2030-11-29
[14 empty] | Weekends | 2030-12-01 | 2030-12-02
[14 empty] | Weekends | 2030-12-07 | 2030-12-06
[14 empty] | Weekends | 2030-12-08 | 2030-12-09
[14 empty] | Weekends | 2030-12-14 | 2030-12-13
[14 empty] | Weekends | 2030-12-15 | 2030-12-16
[14 empty] | Weekends | 2030-12-21 | 2030-12-20
[14 empty] | Weekends | 2030-12-22 | 2030-12-23
[14 empty] | Weekends | 2030-12-28 | 2030-12-27
[14 empty] | Weekends | 2030-12-29 | 2030-12-30
[14 empty] | Holiday | 2024-01-01 | 2024-01-02
[14 empty] | Holiday | 2024-01-15 | 2024-01-16
[14 empty] | Holiday | 2024-02-19 | 2024-02-20
[14 empty] | Holiday | 2024-05-27 | 2024-05-28
[14 empty] | Holiday | 2024-06-19 | 2024-06-20
[14 empty] | Holiday | 2024-07-04 | 2024-07-05
[14 empty] | Holiday | 2024-09-02 | 2024-09-03
[14 empty] | Holiday | 2024-11-14 | 2024-11-15
[14 empty] | Holiday | 2024-11-11 | 2024-11-12
[14 empty] | Holiday | 2024-11-28 | 2024-11-25
[14 empty] | Holiday | 2024-12-23 | 2024-12-20
[14 empty] | Holiday | 2024-12-24 | 2024-12-20
[14 empty] | Holiday | 2024-12-25 | 2024-12-20
[14 empty] | Holiday | 2024-12-26 | 2024-12-20
[14 empty] | Holiday | 2024-12-27 | 2025-01-06
[14 empty] | Holiday | 2024-12-30 | 2025-01-06
[14 empty] | Holiday | 2025-01-01 | 2025-01-06
[14 empty] | Holiday | 2025-01-02 | 2025-01-06
[14 empty] | Holiday | 2025-01-03 | 2025-01-06
[14 empty] | Holiday | 2025-01-20 | 2025-01-21
[14 empty] | Holiday | 2025-02-17 | 2025-02-18
[14 empty] | Holiday | 2025-05-16 | 2025-05-15
[14 empty] | Holiday | 2025-06-19 | 2025-06-18
[14 empty] | Holiday | 2025-07-04 | 2025-07-03
[14 empty] | Holiday | 2025-09-01 | 2025-09-02
[14 empty] | Holiday | 2025-10-13 | 2025-10-14
[14 empty] | Holiday | 2025-11-11 | 2025-11-12
[14 empty] | Holiday | 2025-11-27 | 2025-11-24
[14 empty] | Holiday | 2025-12-22 | 2025-12-19
[14 empty] | Holiday | 2025-12-23 | 2025-12-19
[14 empty] | Holiday | 2025-12-24 | 2025-12-19
[14 empty] | Holiday | 2025-12-25 | 2025-12-19
[14 empty] | Holiday | 2025-12-26 | 2025-12-19
[14 empty] | Holiday | 2025-12-29 | 2026-01-05
[14 empty] | Holiday | 2025-12-30 | 2026-01-05
[14 empty] | Holiday | 2025-12-31 | 2026-01-05
[14 empty] | Holiday | 2026-01-01 | 2026-01-05
[14 empty] | Holiday | 2026-01-02 | 2026-01-05
[14 empty] | Holiday | 2026-01-19 | 2026-01-20
[14 empty] | Holiday | 2026-02-16 | 2026-02-17
[14 empty] | Holiday | 2026-05-25 | 2026-05-26
[14 empty] | Holiday | 2026-06-19 | 2026-06-18
[14 empty] | Holiday | 2026-07-03 | 2026-07-02
[14 empty] | Holiday | 2026-09-07 | 2026-09-08
[14 empty] | Holiday | 2026-10-12 | 2026-10-13
[14 empty] | Holiday | 2026-11-11 | 2026-11-12
[14 empty] | Holiday | 2026-11-26 | 2026-11-23
[14 empty] | Holiday | 2026-12-21 | 2026-12-18
[14 empty] | Holiday | 2026-12-22 | 2026-12-18
[14 empty] | Holiday | 2026-12-23 | 2026-12-18
[14 empty] | Holiday | 2026-12-24 | 2026-12-18
[14 empty] | Holiday | 2026-12-25 | 2026-12-18
[14 empty] | Holiday | 2026-12-28 | 2027-01-04
[14 empty] | Holiday | 2026-12-29 | 2027-01-04
[14 empty] | Holiday | 2026-12-30 | 2027-01-04
[14 empty] | Holiday | 2026-12-31 | 2027-01-04
[14 empty] | Holiday | 2027-01-01 | 2027-01-04
[14 empty] | Holiday | 2027-01-18 | 2027-01-19
[14 empty] | Holiday | 2027-02-15 | 2027-02-16
[14 empty] | Holiday | 2027-05-31 | 2027-06-01
[14 empty] | Holiday | 2027-06-18 | 2027-06-17
[14 empty] | Holiday | 2027-07-05 | 2027-07-06
[14 empty] | Holiday | 2027-09-06 | 2027-09-07
[14 empty] | Holiday | 2027-10-11 | 2027-10-12
[14 empty] | Holiday | 2027-11-11 | 2027-11-10
[14 empty] | Holiday | 2027-11-25 | 2027-11-22
[14 empty] | Holiday | 2027-12-20 | 2027-12-17
[14 empty] | Holiday | 2027-12-21 | 2027-12-17
[14 empty] | Holiday | 2027-12-22 | 2027-12-17
[14 empty] | Holiday | 2027-12-23 | 2027-12-17
[14 empty] | Holiday | 2027-12-24 | 2027-12-17
[14 empty] | Holiday | 2027-12-27 | 2028-01-03
[14 empty] | Holiday | 2027-12-28 | 2028-01-03
[14 empty] | Holiday | 2027-12-29 | 2028-01-03
[14 empty] | Holiday | 2027-12-30 | 2028-01-03
[14 empty] | Holiday | 2027-12-31 | 2028-01-03
[14 empty] | Holiday | 2028-01-17 | 2028-01-18
[14 empty] | Holiday | 2028-02-21 | 2028-02-22
[14 empty] | Holiday | 2028-05-29 | 2028-05-30
[14 empty] | Holiday | 2028-06-19 | 2028-06-20
[14 empty] | Holiday | 2028-07-04 | 2028-07-05
[14 empty] | Holiday | 2028-09-04 | 2028-09-05
[14 empty] | Holiday | 2028-10-09 | 2028-10-10
[14 empty] | Holiday | 2028-11-10 | 2028-11-09
[14 empty] | Holiday | 2028-11-23 | 2028-11-20
[14 empty] | Holiday | 2028-12-25 | 2028-12-22
[14 empty] | Holiday | 2028-12-26 | 2028-12-22
[14 empty] | Holiday | 2028-12-27 | 2028-12-22
[14 empty] | Holiday | 2028-12-28 | 2028-12-22
[14 empty] | Holiday | 2028-12-29 | 2028-12-22
[14 empty] | Holiday | 2029-01-01 | 2029-01-08
[14 empty] | Holiday | 2029-01-02 | 2029-01-08
[14 empty] | Holiday | 2029-01-03 | 2029-01-08
[14 empty] | Holiday | 2029-01-04 | 2029-01-08
[14 empty] | Holiday | 2029-01-05 | 2029-01-08
[14 empty] | Holiday | 2029-01-15 | 2029-01-16
[14 empty] | Holiday | 2029-02-19 | 2029-02-20
[14 empty] | Holiday | 2029-05-28 | 2029-05-29
[14 empty] | Holiday | 2029-06-19 | 2029-06-20
[14 empty] | Holiday | 2029-07-04 | 2029-07-05
[14 empty] | Holiday | 2029-09-03 | 2029-09-04
[14 empty] | Holiday | 2029-10-08 | 2029-10-09
[14 empty] | Holiday | 2029-11-12 | 2029-11-13
[14 empty] | Holiday | 2029-11-22 | 2029-11-19
[14 empty] | Holiday | 2029-12-24 | 2029-12-21
[14 empty] | Holiday | 2029-12-25 | 2029-12-21
[14 empty] | Holiday | 2029-12-26 | 2029-12-21
[14 empty] | Holiday | 2029-12-27 | 2029-12-21
[14 empty] | Holiday | 2029-12-28 | 2029-12-21
[14 empty] | Holiday | 2029-12-31 | 2030-01-07
[14 empty] | Holiday | 2030-01-01 | 2030-01-07
[14 empty] | Holiday | 2030-01-02 | 2030-01-07
[14 empty] | Holiday | 2030-01-03 | 2030-01-07
[14 empty] | Holiday | 2030-01-04 | 2030-01-07
[14 empty] | Holiday | 2030-01-21 | 2030-01-22
[14 empty] | Holiday | 2030-02-18 | 2030-02-19
[14 empty] | Holiday | 2030-05-27 | 2030-05-28
[14 empty] | Holiday | 2030-06-19 | 2030-06-18
[14 empty] | Holiday | 2030-07-04 | 2030-07-03
[14 empty] | Holiday | 2030-09-02 | 2030-09-03
[14 empty] | Holiday | 2030-11-14 | 2030-11-13
[14 empty] | Holiday | 2030-11-11 | 2030-11-12
[14 empty] | Holiday | 2030-11-28 | 2030-11-25
[14 empty] | Holiday | 2030-12-23 | 2030-12-20
[14 empty] | Holiday | 2030-12-24 | 2030-12-20
[14 empty] | Holiday | 2030-12-25 | 2030-12-20
Cost Product Timeline Planner Tool
For questions please contact Nicholas Cesare nicholas.a.cesare2.civ@army.mil
Must enter data from top down

## Hidden (hidden)
[27 empty] | Static Len | Allowed Len Per | Total Len
Schedule Matrix | [7 empty] | MCA DBS Army Delegated |  | MCA DBS Non Army Delegated |  | RFP Army Delegated |  | RFP Non Army Delegated |  | MTA Army Delegated |  | MTA Non Army Delegated |  | SWP | [6 empty] | 173 | 13.6667 | 107 |  |  |  | mailto:usarmy.belvoir.hqda-asa-fm.list.dasa-ce-crb-office@army.mil?subject=Notification of Upcoming Estimate&body=0 (0)%0d%0a: (0 - 0)%0d%0a01/00/00%0d%0a%0d%0a0%0d%0a0%0d%0a0
Major Capability Acquisition (MCA; DoDI 5000.85) Milestone A (MS A) AAE | 3 |  |  | I |  | A&S | 3 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 21 | 22 | 23 | 24 | 30 | 31 | 32 | 33 | 40 | 41 | mailto: | usarmy.belvoir.hqda-asa-fm.list.dasa-ce-crb-office@army.mil |  | Major Capability Acquisition (MCA; DoDI 5000.85) | MCA | Milestone A (MS A) | MS A | 176 | Application
Major Capability Acquisition (MCA; DoDI 5000.85) Milestone B (MS B) AAE | 3 |  |  | II |  | AAE | 1 | Army Cost Position Development Timeline Planner Army Delegated ACAT I/Special Interest MS A, B, C FRP Army Delegated BCAT I/Special Interest Acq ATP, Fn ATP LD ATP, FD ATP, CS ATP |  | Army Cost Position Development Timeline Planner Army Delegated ACAT I/Special Interest MS A, B, C FRP Army Delegated BCAT I/Special Interest Acq ATP, Fn ATP, LD ATP, FD ATP, CS ATP |  | Draft Army Cost Position Development Timeline Planner (ACAT IB/C) |  | Draft Army Cost Position Development Timeline Planner (ACAT ID) |  | Army Cost Estimate Development Timeline Planner (Middle Tier Acquisition RP/Middle Tier Acquisition RF I) MTA Army Delegated |  | Army Cost Estimate Development Timeline Planner (Middle Tier Acquisition RP/ Middle Tier Acquisition RF e) MTA Non-Army Delegated |  | Army Cost Estimate Development Timeline Planner (Software Pathway Execution Decision) |  | Software Acquisition Pathway Cost Growth Sufficiency Review Timeline Planner For ACAT I/II SWP Programs with Cost Growth* |  | Operational Sustainment Review (OSR) Independent Cost Estimate Development Timeline Planner (ACAT I) |  | subject: | Notification of Upcoming Estimate |  | Defense Business System (DBS; DoDI 5000.75) | DBS | Request for Proposal (RFP) Release | RFP | CLICK To Email MS OUTLOOK Must be Open | Embedded
Major Capability Acquisition (MCA; DoDI 5000.85) Milestone C (MS C) AAE | 3 |  |  | III |  | PAE/CPE |  | The DoDI 5000.73 contains timelines developed by OSW CA for submission of documents to support Milestone Reviews and are tied to the OSW OIPT. HQDA and the Program Office must complete the Cost Analysis and Affordability Analysis in time to support the Army OIPT. The dates in this timeline planner were developed to be as consistent as possible with the OSW timelines but provide the Army staff sufficient time to complete the required analyses to inform the Army OIPT. |  | The DoDI 5000.73 contains timelines developed by OSW CA for submission of documents to support Milestone Reviews and are tied to the OSW OIPT. HQDA and the Program Office must complete the Cost Analysis and Affordability Analysis in time to support the Army OIPT. The dates in this timeline planner were developed to be as consistent as possible with the OSW timelines but provide the Army staff sufficient time to complete the required analyses to inform the Army OIPT. |  | DoDI 5000.73 states that OSW CA will meet with representatives from the Service Cost Agency and Program Office no later than 180 calendar days before the scheduled Development RFP Release Decision Point. At this meeting, it will be determined what cost analysis, if any, will be presented at the Decision Point Review and who will be responsible for preparing it. For some programs, the Milestone A ICE will suffice as is or it is updated. In other cases, the cost analysis may be a complete ICE. The DoDI 5000.73 contains timelines developed by OSW CA for submission of documents to support Milestone Reviews and are tied to the OSW OIPT. HQDA and the Program Office must complete the cost analysis and affordability analysis in time to support the Army OIPT. The dates in this timeline planner were developed to be as consistent as possible with the OSW timelines but provide the Army staff sufficient time to complete the required analyses to inform the Army OIPT. |  | DoDI 5000.73 states that OSW CA will meet with representatives from the Service Cost Agency and Program Office no later than 180 calendar days before the scheduled Development RFP Release Decision Point. At this meeting, it will be determined what cost analysis, if any, will be presented at the Decision Point Review and who will be responsible for preparing it. For some programs, the Milestone A ICE will suffice as is or it is updated. In other cases, the cost analysis may be a complete ICE. The DoDI 5000.73 contains timelines developed by OSW CA for submission of documents to support Milestone Reviews and are tied to the OSW OIPT. HQDA and the Program Office must complete the cost analysis and affordability analysis in time to support the Army OIPT. The dates in this timeline planner were developed to be as consistent as possible with the OSW timelines but provide the Army staff sufficient time to complete the required analyses to inform the Army OIPT. |  | The DoDI 5000.73 contains timelines developed by OSW CA for submission of documents to support MTA approval. HQDA and the Program Office must complete the Cost Estimate to support the MTA package submission to the DASM. The dates in this timeline planner were developed to be consistent with current Army policy and support OSW timelines. |  | The DoDI 5000.73 contains timelines developed by OSW CA for submission of documents to support MTA approval. HQDA and the Program Office must complete the Cost Estimate to support the MTA package submission to the DASM. The dates in this timeline planner were developed to be consistent with current Army policy and support OSW timelines. |  | The DoDI 5000.73 contains timelines developed by OSW CA for submission of documents to support the Software Pathway (SWP) Execution Phase (EP) decision. HQDA and the Program Office must complete the Army Cost Estimate (ACE) to support the SWP EP decision. The dates in this timeline planner were developed to be consistent with current Army policy and support OSW timelines. |  | The dates in this timeline planner support a DASA-CE Sufficiency Review for Software Pathway programs that are experiencing cost growth as defined in the ASA(ALT) Software Acquisition Pathway Policy (22 Dec. 2021) |  | The DoDI 5000.73 contains timelines developed by OSW CA for submission of documents to support Sustainment Reviews. DASA-CE and the Program Office must complete the Cost Estimate to support the Operational Sustainment Review. The dates in this timeline planner were developed to be consistent with current Army policy and support OSW timelines. |  | Display Text: | CLICK To Email MS OUTLOOK Must be Open |  | Middle Tier Acquisition Rapid Prototyping (MTA RP; DoDI 5000.80) | MTA RP | Milestone B (MS B) | MS B |  | Defense Business System
Major Capability Acquisition (MCA; DoDI 5000.85) Full Rate Production (FRP) AAE | 3 |  |  | IV |  |  |  | Early Milestone notification to OSW CA is essential because they will decide whether to develop the statutory ICE or delegate it to DASA-CE. CRB ACP Review occurs 90 Days after CPE approved CARD is briefed to the CRB. |  | Early Milestone notification to OSW CA is essential because they will decide whether to develop the statutory ICE or delegate it to DASA-CE. CRB ACP Review occurs 90 Days after CPE approved CARD is briefed to the CRB. |  | The objective is to complete the draft ACP and Affordability Analysis to support Army OIPT. DASA-CE Darft ACP Review occurs 70 Days after Draft CARD is briefed to the CRBWG |  | The objective is to complete the draft ACP and Affordability Analysis to support Army OIPT. DASA-CE Darft ACP Review occurs 70 Days after Draft CARD is briefed to the CRBWG |  | Early Milestone notification to OSW CA is essential because they will decide whether to develop or delegate the regulatory estimate of life-cycle costs for MTA rapid prototyping and fielding programs |  | Early Milestone notification to OSW CA is essential because they will decide whether to develop or delegate the regulatory estimate of life-cycle costs for MTA rapid prototyping and fielding programs |  | Early Milestone notification to OSW CA is essential because they will decide whether to develop or delegate the regulatory independent cost estimate for ACAT I/ACAT II programs pursuing the Software Pathway. Enter desired SWP Execution Phase Approval Date and the rest of the dates will automatically calculate |  |  |  | Early Milestone notification to OSW CA is essential because they will decide whether to develop or delegate the ICE. |  | Program Name: | 0 |  | Middle Tier Acquisition Rapid Fielding (MTA RF; DoDI 5000.80) | MTA RF | Milestone C (MS C) | MS C
Major Capability Acquisition (MCA; DoDI 5000.85) Re-Baseline AAE | 3 | [6 empty] | Notify DASA-CE of Upcoming Milestone | -246 | Notify DASA-CE of Upcoming Milestone | -246 | Notify DASA-CE of Upcoming Milestone | -195 | Notify DASA-CE of Upcoming Milestone | -195 | CPE/PMO notification to DASA-CE CRB | -120 | CPE/PMO notification to DASA-CE CRB | -120 | Notify OSW CA/DASA-CE CRB of upcoming decision* | -210 | Cost Growth Determination | 0 | Notify OSW CA of upcoming OSR (DASA-CE issues Kick-off Memo) | -245 | Capability Program Executive Office (CPE): | 0 |  | Software Acquisition (SWP; DoDI 5000.87) | SWP | Full Rate Production (FRP) | FRP
Major Capability Acquisition (MCA; DoDI 5000.85) Request for Proposal (RFP) Release AAE | 7 | [6 empty] | Notify OSW CA of Upcoming Milestone | -231 | Notify OSW CA of Upcoming Milestone | -231 | PM/CRBWG Cost WIPT with OSW CA | -180 | PM/CRBWG Cost WIPT with OSW CA | -180 | DASA-CE issued Kick-off Memo* | -115 | DASA-CE issued Kick-off Memo* | -115 | DASA-CE issued Kick-off Memo | -205 | Notify DASA-CE/ASA(ALT) of Cost Growth Determination | 10 | DASA-CE Cat A/B Cost Estimate Identification | -235 | Pathway: |  |  |  |  | Re-Baseline | Re-Base
Major Capability Acquisition (MCA; DoDI 5000.85) Operational Sustainment Review (OSR) AAE | 40 | [6 empty] | PM/CRBWG Cost WIPT with OSW CA | -222 | PM/CRBWG Cost WIPT with OSW CA | -222 | Draft CARD Submission to ASA(ALT) | -130 | Draft CARD Submission to ASA(ALT) | -130 | PM/CRBWG Cost WIPT with OSW CA/Draft Program Description Briefing** | -110 | PM/CRBWG Cost WIPT with OSW CA/Draft Program Description Briefing** | -110 | PM/CRBWG Cost WIPT with OSW CA/ Draft CARD delivered to ASA(ALT)/DASA-CE/OSW CA | -180 | Submission of POE, updated CARD, and supporting documentation to include software metrics | 20 | OSR Kick-off | -220 | Event Estimate Support: |  |  |  |  | Operational Sustainment Review (OSR) | OSR
Major Capability Acquisition (MCA; DoDI 5000.85) Milestone A (MS A) A&S | 5 | [6 empty] | Draft CARD Submitted to ASA(ALT)/DASA-CE/OSW CA | -201 | Draft CARD Submitted to ASA(ALT)/DASA-CE/OSW CA | -201 | CARD & POE Briefing to CRB Working Group | -90 | CARD & POE Briefing to CRB Working Group | -90 | CPE-Signed Program Description (CARD/CARD-like Document) to ASA(ALT) for Staffing | -105 | CPE-Signed Program Description (CARD/CARD-like Document) to ASA(ALT) for Staffing | -105 | OSW CA Determination to Review Component ICE or Prepare CA ICE | -165 | Cost IPT to review updated estimate and software metrics | 34 | Draft CARD Submitted | -200 | ACAT/BCAT Equivalent: | 0 |  |  |  | Functional Requirements ATP | FR ATP
Major Capability Acquisition (MCA; DoDI 5000.85) Milestone B (MS B) A&S | 5 | [6 empty] | OSW CA Determination to Review Component ICE or Prepare OSW CA ICE | -186 | CPE-Approved CARD Submission to ASA(ALT) | -149 | CRB Working Group Kick-Off (Draft ACP presented to CRBWG/CA) | -40 | CRB Working Group Kick-Off (Draft ACP presented to CRBWG/CA) | -40 | First Submission of POE | -105 | First Submission of POE | -105 | CPE Signed CARD/CARD-like document to ASA(ALT) for Staffing | -105 | Sufficiency Review (SR) Results Briefing to DASA-CE | 80 | Acquisition/Cost WIPT with DASA-CE, DASA-S, and OSW CA | -200 | Decision Authority: | 0 |  |  |  | Limited Deployment ATP | LD ATP
Major Capability Acquisition (MCA; DoDI 5000.85) Milestone C (MS C) A&S | 5 | [6 empty] | CPE-Approved CARD Submission to ASA(ALT) | -149 | CARD Briefing to CRB Working Group | -121 | Draft ACP Presented to the DASA-CE | -20 | Draft ACP Presented to the DASA-CE | -20 | POE Briefing to limited CRBWG members | -100 | POE Briefing to limited CRBWG members | -100 | Initial POE Submission | -105 | DASA-CE issues Sufficiency Review Memo | 85 | OSW CA Determination to Review Component ICE or Prepare OSW CA ICE | -185 | UPDATES BASED ON ABOVE | 01/00/00 |  |  |  | Acquisition ATP | Acq ATP
Major Capability Acquisition (MCA; DoDI 5000.85) Full Rate Production (FRP) A&S | 5 | [6 empty] | CARD Briefing to CRB Working Group | -121 | CCE Methodology Briefing to DASA-CE | -113 | Army OIPT | 0 | Army OIPT | 0 | DASA-CE Determination to perform Full CCE or Limited CCE | -95 | DASA-CE Determination to perform Full CCE or Limited CCE | -95 | POE Briefing to limited CRBWG members | -100 | Final documentation uploaded to CPP | 85 | CPE-Approved CARD Submission to ASA(ALT) for Staffing | -150 | Total Estimated Dollar Value in $M (specify years included in estimate): |  |  |  |  | Entrance | Enter
Major Capability Acquisition (MCA; DoDI 5000.85) Re-Baseline A&S | 5 | [6 empty] | CCE/ICE Methodology Briefing to DASA-CE/OSW CA | -113 | CARD Briefing to CRB Principals | -111 | ASARC | 42 | OSW OIPT | 21 | Final Program Description Submission to DASA-CE post comment adjudication | -90 | Final Program Description Submission to DASA-CE post comment adjudication | -90 | Updated CARD (CARD/CARD-like document) to DASA-CE post comment adjudication | -90 |  |  | Submission of POE to DASA-CE | -125 | Base Year of Total Estimated Dollar Value: | 0 |  |  |  | Entrance | Enter
Major Capability Acquisition (MCA; DoDI 5000.85) Request for Proposal (RFP) Release A&S | 9 | [6 empty] | CARD Briefing to CRB Principals | -111 | Deliver CARD with CRB Updates to OSW CA | -66 |  |  | ASARC | 42 | CCE Methodology brief to DASA-CE | -90 | CCE Methodology brief to DASA-CE | -90 | ICE Methodology Briefing to DASA-CE | -90 |  |  | POE Briefing to DASA-CE | -125 | Program Management Office Point of Contact: | 0 |  |  |  | Execution Phase | Ex Phs
Major Capability Acquisition (MCA; DoDI 5000.85) Operational Sustainment Review (OSR) A&S | 40 | [6 empty] | Deliver CARD with CRB Updates to OSW CA | -66 | CCE Results Briefing to DASA-CE | -61 |  |  | DAB | 56 | Program Description Briefing to CRB Working Group | -85 | Program Description Briefing to CRB Working Group | -85 | CARD/CARD-like document Briefing to CRBWG | -82 |  |  | ICE Methodology Briefing to DASA-CE | -122 | If SWP Growth Notification, Delta between Original and Current Estimate in BY $M: | 0 |  |  |  | Cost Growth | $ Grow
Major Capability Acquisition (MCA; DoDI 5000.85) Milestone A (MS A) PAE/CPE | 3 | [6 empty] | CCE/ICE Results Briefing to DASA-CE/OSW CA | -61 | POE/CCE Submission | -58 |  |  |  |  | Program Description Briefing to CRB Principals | -75 | Program Description Briefing to CRB Principals | -75 | CARD (CARD/CARD-like document) Briefing to CRB Principals | -75 |  |  | CARD brief to Army Principals and OSW CA | -120
Major Capability Acquisition (MCA; DoDI 5000.85) Milestone B (MS B) PAE/CPE | 3 | [6 empty] | POE and CCE/ICE Submission | -58 | CRB Working Group Kick-Off (POE/CCE presented to CRBWG) | -51 |  |  |  |  | CCE Estimate Results brief to DASA-CE | -58 | CCE Estimate Results brief to DASA-CE | -58 | ICE Estimate Results brief to DASA-CE | -58 |  |  | OSR IPR 1 | -110
Major Capability Acquisition (MCA; DoDI 5000.85) Milestone C (MS C) PAE/CPE | 3 | [6 empty] | CRB Working Group Kick-Off (POE/ICE presented to CRBWG/CA) | -51 | Recommended ACP Briefing to DASA-CE | -27 |  |  |  |  | Second POE/CCE Estimate Submission | -55 | Second POE/CCE Estimate Submission | -55 | Final POE Submission; ICE Submission | -55 |  |  | Draft ICE Results/Category A/B Briefing to Army Principals and OSW CA | -70
Major Capability Acquisition (MCA; DoDI 5000.85) Full Rate Production (FRP) PAE/CPE | 3 | [6 empty] | Recommended ACP Briefing to DASA-CE | -27 | Recommended ACP Briefing to CRB Principals | -21 |  |  |  |  | CRB Working Group Kickoff | -50 | CRB Working Group Kickoff | -50 | CRB Working Group Kickoff | -50 |  |  | OSR IPR 2 (Includes Draft ICE) | -50
Major Capability Acquisition (MCA; DoDI 5000.85) Re-Baseline PAE/CPE | 3 | [6 empty] | Recommended ACP Briefing to CRB Principals | -21 | Compare ACP to OSW CA ICE | -14 |  |  |  |  | Recommended Draft Army Cost Estimate (ACE) to DASA-CE | -35 | Recommended Draft Army Cost Estimate (ACE) to DASA-CE | -35 | Recommended Draft Army Cost Estimate (ACE) to DASA-CE | -35 |  |  | ICE Reconciliation Working Group Start | -50
Major Capability Acquisition (MCA; DoDI 5000.85) Request for Proposal (RFP) Release PAE/CPE | 7 | [6 empty] | Deliver CRB-Reviewed ACP and ICE to OSW CA | -18 | Army OIPT | 0 |  |  |  |  | Recommended ACE/Affordability Assessment to CRB Principals | -33 | Recommended ACE/Affordability Assessment to CRB Principals | -33 | ACE/Affordability Assessment to CRB Principals | -33 |  |  | Final ICE Results Briefing to DASA-CE, DASA-S, and OSW CA | -25
Major Capability Acquisition (MCA; DoDI 5000.85)Operational Sustainment Review (OSR) PAE/CPE | 40 | [6 empty] | AAE ACP/ICE Review with PM, DASA-CE and OSW CA (If reqd) | -7 | OSW OIPT | 28 |  |  |  |  | MTA package sent to DASM | -30 | MTA package sent to DASM | -30 | Software Pathway package sent to DASM/CPE, including ACE** | -30 |  |  | ICE Results to OSW CA | -15
Defense Business System (DBS; DoDI 5000.75) Functional Requirements ATP AAE | 3 | [6 empty] | Army OIPT | 0 | Deliver ASA(FM&C) Approved ACP (FM&C Memo/CAB/Affordability Memo) | 29 |  |  |  |  | Update ACE, if required | -5 | Update ACE, if required | -5 | Update ACE, if required | -7 |  |  | Updated Signed CARD Addendum | -10
Defense Business System (DBS; DoDI 5000.75) Limited Deployment ATP AAE | 3 | [6 empty] | ASARC | 42 | ASARC | 42 |  |  |  |  | AAE MTA Approval | 0 | AAE MTA Approval | 0 | Deliver ACE to OSW CA*** | -7 |  |  | OSR | 0
Defense Business System (DBS; DoDI 5000.75) Acquisition ATP AAE | 3 | Major Capability Acquisition (MCA; DoDI 5000.85) | Defense Business System (DBS; DoDI 5000.75) | Middle Tier Acquisition Rapid Prototyping (MTA RP; DoDI 5000.80) | Middle Tier Acquisition Rapid Fielding (MTA RF; DoDI 5000.80) | Software Acquisition (SWP; DoDI 5000.87) |  |  |  | DAB | 56 |  |  |  |  | Deliver ACE to OSW CA | 1e-21 | Final ACE documentation*** uploaded to CPP, to include final Program Description | 10 | Software Pathway Execution Approval | 0 |  |  | ICE Memo/CAB complete | 14
Defense Business System (DBS; DoDI 5000.75) Full Deployment ATP AAE | 3 | Milestone A (MS A) | Functional Requirements ATP | Entrance | Entrance | Execution Phase | [9 empty] | Final ACE documentation*** uploaded to CPP, to include final Program Description | 10 | Cost WIPT with CA, if requested by CA | 14 | Final documentation uploaded to CPP, to include Final Program Description (CARD/CARD-like document) | 10
Defense Business System (DBS; DoDI 5000.75) Functional Requirements ATP A&S | 5 | Request for Proposal (RFP) Release | Limited Deployment ATP |  |  | Cost Growth | [11 empty] | OSW CA Submission of Estimate of Life-Cycle Costs | 60
Defense Business System (DBS; DoDI 5000.75) Limited Deployment ATP A&S | 5 | Milestone B (MS B) | Acquisition ATP
Defense Business System (DBS; DoDI 5000.75) Acquisition ATP A&S | 5 | Milestone C (MS C) | Full Deployment ATP
Defense Business System (DBS; DoDI 5000.75) Full Deployment ATP A&S | 5 | Full Rate Production (FRP) | Capability Support ATP
Defense Business System (DBS; DoDI 5000.75) Functional Requirements ATP PAE/CPE | 3 | Re-Baseline
Defense Business System (DBS; DoDI 5000.75) Limited Deployment ATP PAE/CPE | 3 | Operational Sustainment Review (OSR)
Defense Business System (DBS; DoDI 5000.75) Acquisition ATP PAE/CPE | 3
Defense Business System (DBS; DoDI 5000.75) Full Deployment ATP PAE/CPE | 5 | [6 empty] | The Draft CARD submitted to ASA(ALT)/DASA-CE/OSW CA 180 days prior to the CRB (201 days prior to the Army OIPT) does not require CPE signature. The CARD submitted to ASA(ALT) 128 days prior to the CRB (149 days prior to the Army OIPT) does require CPE signature DoDI 5000.73 bases dates on the OSW OIPT, these dates are based on the Army OIPT OSW CA - Cost Assessment Directorate of OSW CAPE ICE - Independent Cost Estimate CCA - Component Cost Assessment |  | The Draft CARD submitted to ASA(ALT)/DASA-CE/OSW CA 180 days prior to the CRB (201 days prior to the Army OIPT) does not require PEO signature. The CARD submitted to ASA(ALT) 128 days prior to the CRB (149 days prior to the Army OIPT) does require PEO signature DoDI 5000.73 bases dates on the OSW OIPT, these dates are based on the Army OIPT OSW CA - Cost Assessment Directorate of OSW CAPE ICE - Independent Cost Estimate CCA - Component Cost Assessment |  | The Draft CARD submitted to ASA(ALT)/DASA-CE/OSW CA 130 days prior to the Army OIPT does not require CPE signature. DoDI 5000.73 bases dates on the RFP Release Review Decision date, these dates are based on the Army OIPT OSW CA - Cost Assessment Directorate of OSW CAPE ICE - Independent Cost Estimate CCA - Component Cost Assessment |  | The Draft CARD submitted to ASA(ALT)/DASA-CE/OSW CA 130 days prior to the Army OIPT does not require CPE signature. DoDI 5000.73 bases dates on the RFP Release Review Decision date, these dates are based on the Army OIPT OSW CA - Cost Assessment Directorate of OSW CAPE ICE - Independent Cost Estimate CCA - Component Cost Assessment |  | * Kick-off memo will include the MTA Cost Estimate Timeline and specific data requests. ** PMO will brief the draft Program Description at the Cost WIPT to gain feedback on tailored contents. Program Description (CARD-like) document will be tailored at the discretion of the Cost WIPT, and will include: Program Overview and Status, Requirements, Acquisition Strategy, Program Schedule, Major Components, Software Sizing, Time-phased Qty, Test Description/Schedule, GFE, Sustaiment Concept (Interim Contractor Logistic Support scope & duration, FSR/LAR, transition dates to TT/SS PEGs, etc), Manpower, and Training. *** Final ACE timeline is notional and may be dependent on Governance Board schedule and contract award timelines. OSW CA - Cost Assessment Directorate of OSW CAPE POE - Program Cost Estimate CCE - Component Cost Estimate |  | * Kick-off memo will include the MTA Cost Estimate Timeline and specific data requests. ** Acquisition Strategy, Program Schedule, Major Components, Software Sizing, Time-phased Qty, Test Description/Schedule, GFE, Sustaiment Concept (Interim Contractor Logistic Support scope & duration, FSR/LAR, transition dates to TT/SS PEGs, etc), Manpower, and Training. *** Final ACE timeline is notional and may be dependent on Governance Board schedule and contract award timelines. OSW CA - Cost Assessment Directorate of OSW CAPE POE - Program Cost Estimate CCE - Component Cost Estimate |  | * Per the DoDI 5000.73 and ASA(ALT) policy, the PM/CPE is also required to notify OSW CA and DASA-CE once the program enters the planning phase. If the start of the planning phase is less than 210 days prior to the EP, the timeline will be tailored accordingly. If the program intends to skip the planning phase, notification occurs when the decision to skip the phase is made. Notification must occur NLT 120 days from Execution decision. Official notification to DASA-CE follows the notification instructions in the FM&C SWP Cost Policy Memo. ** Submission to DASM applicable if AAE is the DA *** ACE serves as OSW CA-delegated estimate OSW CA - Cost Assessment Directorate of OSW CAPE POE - Program Cost Estimate ACE - Army Cost Estimate |  | * Cost growth is defined in the ASA(ALT) Software Acquisition Pathway Policy (22 Dec. 2021) and is defined as: i) A percent increase in the total estimate over the FYDP of at least 15% over the previous estimate; ii) A percent increase in the estimate of any previously estimated year of at least 30%
Defense Business System (DBS; DoDI 5000.75) Capability Support ATP AAE | 3
Defense Business System (DBS; DoDI 5000.75) Capability Support ATP A&S | 5
Defense Business System (DBS; DoDI 5000.75) Capability Support ATP PAE/CPE | 3
Middle Tier Acquisition Rapid Fielding (MTA RF; DoDI 5000.80) Entrance AAE | 21
Middle Tier Acquisition Rapid Prototyping (MTA RP; DoDI 5000.80) Entrance AAE | 21 | [15 empty] | -90 | -120
Middle Tier Acquisition Rapid Fielding (MTA RF; DoDI 5000.80) Entrance PAE/CPE | 21 | [15 empty] | -85 | -115
Middle Tier Acquisition Rapid Prototyping (MTA RP; DoDI 5000.80) Entrance PAE/CPE | 21 | [15 empty] | -80 | -110
Middle Tier Acquisition Rapid Fielding (MTA RF; DoDI 5000.80) Entrance A&S | 23 | [15 empty] | -75 | -105
Middle Tier Acquisition Rapid Prototyping (MTA RP; DoDI 5000.80) Entrance A&S | 23 | [15 empty] | -75 | -105
Software Acquisition (SWP; DoDI 5000.87) Execution Phase AAE | 30 | [15 empty] | -70 | -100
Software Acquisition (SWP; DoDI 5000.87) Cost Growth AAE | 32 | [15 empty] | -65 | -95
Software Acquisition (SWP; DoDI 5000.87) Execution Phase PAE/CPE | 30 | [15 empty] | -60 | -90
Software Acquisition (SWP; DoDI 5000.87) Cost Growth PAE/CPE | 32 | [15 empty] | -60 | -90
Software Acquisition (SWP; DoDI 5000.87) Execution Phase A&S | 30 | [15 empty] | -55 | -85
Software Acquisition (SWP; DoDI 5000.87) Cost Growth A&S | 32 | [15 empty] | -45 | -75
[17 empty] | -28 | -58
[17 empty] | -25 | -55
[17 empty] | -20 | -50
| 2020 | [15 empty] | -5 | -35
| 2021 | [15 empty] | -3 | -33
| 2022 | [15 empty] | 0 | -30
| 2023 | [15 empty] | 25 | -5
| 2024 | [15 empty] | 30 | 0
| 2025 | [15 empty] | 40 | 10
| 2026 | [15 empty] | 44 | 14
| 2027 | [15 empty] | 90 | 60
2028
2029
2030
2031
2032
2033
2034
2035
2036
2037
2038
2039
2040
2041
2042
2043
2044
2045
2046
2047
2048
2049
2050
2051
2052
2053
2054
2055
2056
2057
2058
2059
2060
2061
2062
2063
2064
2065
2066
2067
2068
2069
2070
2071
2072
2073
2074
2075
2076
2077
2078
2079
2080
2081
2082
2083
2084
2085
2086
2087
2088
2089
2090
2091
2092
2093
2094
2095
2096
2097
2098
2099
2100
2101
2102
2103
2104
2105
2106
2107
2108
2109
2110
2111
2112
2113
2114
2115
2116
2117
2118
2119
2120
2121
2122
2123
2124
2125
2126
2127
2128
2129
2130
2131
2132
2133
2134
2135
2136
2137
2138
2139
2140
2141
2142
2143
2144
2145
2146
2147
2148
2149
2150
2151
2152
2153
2154
2155
2156
2157
2158
2159
2160
2161
2162
2163
2164
2165
2166
2167
2168
2169
2170
2171
2172
2173
2174
2175
2176
2177
2178
2179
2180
2181
2182
2183
2184
2185
2186
2187
2188
2189
2190
2191
2192
2193
2194
2195
2196
2197
2198
2199
2200
2201
2202
2203
2204
2205
2206
2207
2208
2209
2210
2211
2212
2213
2214
2215
2216
2217
2218
2219
2220
2221
2222
2223
2224
2225
2226
2227
2228
2229
2230
2231
2232
2233
2234
2235
2236
2237
2238
2239
2240
2241
2242
2243
2244
2245
2246
2247
2248
2249
2250
2251
2252
2253
2254
2255
2256
2257
2258
2259
2260
2261
2262
2263
2264
2265
2266
2267
2268
2269
2270
2271
2272
2273
2274
2275
2276
2277
2278
2279
2280
2281
2282
2283
2284
2285
2286
2287
2288
2289
2290
2291
2292
2293
2294
2295
2296
2297
2298
2299
2300
2301
2302
2303
2304
2305
2306
2307
2308
2309
2310
2311
2312
2313
2314
2315
2316
2317
2318
2319
2320
2321
2322
2323
2324
2325
2326
2327
2328
2329
2330
2331
2332
2333
2334
2335
2336
2337
2338
2339
2340
2341
2342
2343
2344
2345
2346
2347
2348
2349
2350
2351
2352
2353
2354
2355
2356
2357
2358
2359
2360
2361
2362
2363
2364
2365
2366
2367
2368
2369
2370
2371
2372
2373
2374
2375
2376
2377
2378
2379
2380
2381
2382
2383
2384
2385
2386
2387
2388
2389
2390
2391
2392
2393
2394
2395
2396
2397
2398
2399
2400

## Notes
V2
correct Nrief in SWP
V3
removed drop down acronyms
add helpful format for meta data
made SW field N/A if not required
fixed potato with hard validation error
v4
skip
v5
added back email easy button
correct MTA RF data of error D15
clean up hiddened in v6 depending on final email easy button solution
v6
added enable content notification
added POC
v20220218
removed ASAR Distro
Add Full Deployment ATP to timelines for DBSs
Fixed SWP Growth notification
update OSR time line to timeline for Jenna on 14 Feb 2021 email
V20220407
update OSR time line to timeline for Jenna on 05Apr2022 email
v20221122
update OSR timeline to add CA to draft ICE brief
update to add space in header d27
v20230215
update column G to correct spelling error
update to add Capability Support ATP to DBS
v20230314
updated OSR based on email on 3/14/2023 from Shawn Niemi
V20230410
update OSR Based on email form Shawn Niemi on 7 April 2023
v20231213
added logical for weekend and holiday blackout dates Wray request (only goes 2030)
added more details on POE for ACAT level
V20231215
added more details on estimates in meta data
remove the email link
V20240205
added DoDI references to pathway names
update SWP to have three sub types
update to required fields
update to dynamic field for SW Growth and SWP Sub path
Cleaned up LCCE and Acq pathway based on Wray
V20240221
Pat update formatting of number for years and dollar values
V20260601
Update to CPE and PAE verbiage
Pat added chart for ACAT level base on NDAA 2026